## BoQ1
Government eProcurement System Created By: Abhijit Jagannath Created Date/Time: 14-Jul-2026 06:45 PM Tender Title: Project Management Consultancy Services for Development of Greenfield Airport at Great Nicobar Island (GNI), Andaman and Nicobar Islands Tender ID: 2025_AAI_251685_2
Tender Inviting Authority: Senior Manager (Engg. -Civil) (Bid Manager), Airports Authority of India O/o Executive Director (Engg.) MIS and Standardization, Corporate Head Quarters, A-Block, Ground Floor, Rajiv Gandhi Bhawan, Safdarjang Airport, New Delhi-110 003
Name of Work:Project Management Consultancy Services for Development of Greenfield Airport at Great Nicobar Island (GNI), Andaman & Nicobar Islands
Contract No: TENDER ID: 2025_AAI_251685_2
SCHEDULE OF WORK / ITEM(S)
Sl.No | Description of Work / Item(s) | No.of Qty | Units | Estimated Rate | SYSTRA MVA Consulting (India) Private Limited (GSTN-07AAJCS4736M1ZT) BID ID -1008253
[5 empty] | Rate | Amount | L1 Amount | L1 Vendor
1.00 | Part-A
1.01 | Design & Pre-Construction Stage upto award of EPC contracts | 1.00 | JOB |  | 1117639759.00 | 1117639759.00 | 1117639759.00 | SYSTRA MVA Consulting (India) Private Limited
2.00 | Part B - Miscellaneous Expenditure
2.01 | Project Duration | 44.00 | Month |  | 4151264.00 | 182655616.00 | 182655616.00 | SYSTRA MVA Consulting (India) Private Limited
2.02 | Finalization of contract | 6.00 | Month |  | 6500771.00 | 39004626.00 | 39004626.00 | SYSTRA MVA Consulting (India) Private Limited
3.00 | Part C - Supervision staff during Execution stage- Key Personnel
3.01 | Principal Architect | 2.00 | Month |  | 2200000.00 | 4400000.00 | 4400000.00 | SYSTRA MVA Consulting (India) Private Limited
3.02 | Principal Structural Designer | 2.00 | Month |  | 2200000.00 | 4400000.00 | 4400000.00 | SYSTRA MVA Consulting (India) Private Limited
3.03 | Principal MEP Designer | 2.00 | Month |  | 1950000.00 | 3900000.00 | 3900000.00 | SYSTRA MVA Consulting (India) Private Limited
3.04 | Pavement / Highway Engineer - I | 2.00 | Month |  | 2200000.00 | 4400000.00 | 4400000.00 | SYSTRA MVA Consulting (India) Private Limited
3.05 | Material Engineer Cum Geotechnical Engineer - I | 18.00 | Month |  | 2200000.00 | 39600000.00 | 39600000.00 | SYSTRA MVA Consulting (India) Private Limited
3.06 | Project Manager | 44.00 | Months |  | 2200000.00 | 96800000.00 | 96800000.00 | SYSTRA MVA Consulting (India) Private Limited
3.07 | Pavement/ Highway Engineer - II | 22.00 | Month |  | 2200000.00 | 48400000.00 | 48400000.00 | SYSTRA MVA Consulting (India) Private Limited
3.08 | Material Engineer Cum Geotechnical Engineer - II | 22.00 | Month |  | 2200000.00 | 48400000.00 | 48400000.00 | SYSTRA MVA Consulting (India) Private Limited
3.09 | MEP Engineer | 20.00 | Month |  | 1950000.00 | 39000000.00 | 39000000.00 | SYSTRA MVA Consulting (India) Private Limited
3.10 | Survey Engineer | 88.00 | Month |  | 1200000.00 | 105600000.00 | 105600000.00 | SYSTRA MVA Consulting (India) Private Limited
4.00 | Part C - Supervision staff during Execution stage- Non-Key Personnel
4.01 | Deputy Project Manager | 44.00 | Month |  | 2000000.00 | 88000000.00 | 88000000.00 | SYSTRA MVA Consulting (India) Private Limited
4.02 | Engineer HVAC | 22.00 | Month |  | 900000.00 | 19800000.00 | 19800000.00 | SYSTRA MVA Consulting (India) Private Limited
4.03 | Engineer Electrical | 88.00 | Month |  | 900000.00 | 79200000.00 | 79200000.00 | SYSTRA MVA Consulting (India) Private Limited
4.04 | Architect | 22.00 | Month |  | 900000.00 | 19800000.00 | 19800000.00 | SYSTRA MVA Consulting (India) Private Limited
4.05 | Civil Engineer | 176.00 | Month |  | 900000.00 | 158400000.00 | 158400000.00 | SYSTRA MVA Consulting (India) Private Limited
4.06 | Senior Engineer Planning | 22.00 | Month |  | 900000.00 | 19800000.00 | 19800000.00 | SYSTRA MVA Consulting (India) Private Limited
4.07 | Engineer Cost Control | 36.00 | Month |  | 900000.00 | 32400000.00 | 32400000.00 | SYSTRA MVA Consulting (India) Private Limited
4.08 | Jr Civil Engineer | 176.00 | Month |  | 700000.00 | 123200000.00 | 123200000.00 | SYSTRA MVA Consulting (India) Private Limited
4.09 | Quality Control (Civil) | 176.00 | Month |  | 900000.00 | 158400000.00 | 158400000.00 | SYSTRA MVA Consulting (India) Private Limited
4.10 | Quality Control (Mechanical/ Electrical) | 44.00 | Month |  | 800000.00 | 35200000.00 | 35200000.00 | SYSTRA MVA Consulting (India) Private Limited
4.11 | Quantity Surveyors – Civil | 22.00 | Month |  | 800000.00 | 17600000.00 | 17600000.00 | SYSTRA MVA Consulting (India) Private Limited
4.12 | Quantity Surveyors - M/E | 22.00 | Month |  | 800000.00 | 17600000.00 | 17600000.00 | SYSTRA MVA Consulting (India) Private Limited
4.13 | Landscape Architect | 12.00 | Month |  | 850000.00 | 10200000.00 | 10200000.00 | SYSTRA MVA Consulting (India) Private Limited
4.14 | Health safety and Environmental Engineer | 22.00 | Month |  | 800000.00 | 17600000.00 | 17600000.00 | SYSTRA MVA Consulting (India) Private Limited
4.15 | Document Controller | 36.00 | Month |  | 500000.00 | 18000000.00 | 18000000.00 | SYSTRA MVA Consulting (India) Private Limited
4.16 | Bim Expert | 12.00 | Month |  | 800000.00 | 9600000.00 | 9600000.00 | SYSTRA MVA Consulting (India) Private Limited
4.17 | Senior Architect | 6.00 | Month |  | 900000.00 | 5400000.00 | 5400000.00 | SYSTRA MVA Consulting (India) Private Limited
4.18 | Senior Structural Designer | 18.00 | Month |  | 1100000.00 | 19800000.00 | 19800000.00 | SYSTRA MVA Consulting (India) Private Limited
4.19 | Senior MEP Designer | 18.00 | Month |  | 1100000.00 | 19800000.00 | 19800000.00 | SYSTRA MVA Consulting (India) Private Limited
4.20 | IT system specialist | 18.00 | Month |  | 1100000.00 | 19800000.00 | 19800000.00 | SYSTRA MVA Consulting (India) Private Limited
4.21 | Project Planner | 18.00 | Month |  | 1100000.00 | 19800000.00 | 19800000.00 | SYSTRA MVA Consulting (India) Private Limited
4.22 | PHE Expert | 18.00 | Month |  | 1100000.00 | 19800000.00 | 19800000.00 | SYSTRA MVA Consulting (India) Private Limited
4.23 | Façade Expert | 18.00 | Month |  | 1200000.00 | 21600000.00 | 21600000.00 | SYSTRA MVA Consulting (India) Private Limited
4.24 | Real Estate / Retail / Commercial Planner Expert | 6.00 | Month |  | 1200000.00 | 7200000.00 | 7200000.00 | SYSTRA MVA Consulting (India) Private Limited
4.25 | GRIHA Specialist | 22.00 | Month |  | 1200000.00 | 26400000.00 | 26400000.00 | SYSTRA MVA Consulting (India) Private Limited
4.26 | Contract cum law specialist | 44.00 | Month |  | 1200000.00 | 52800000.00 | 52800000.00 | SYSTRA MVA Consulting (India) Private Limited
4.27 | Senior Supervision Structural Engineer | 12.00 | Month |  | 1100000.00 | 13200000.00 | 13200000.00 | SYSTRA MVA Consulting (India) Private Limited
4.28 | Senior Supervision Civil Engineer | 36.00 | Month |  | 1100000.00 | 39600000.00 | 39600000.00 | SYSTRA MVA Consulting (India) Private Limited
4.29 | Interior Architect | 12.00 | Month |  | 1100000.00 | 13200000.00 | 13200000.00 | SYSTRA MVA Consulting (India) Private Limited
4.30 | Senior Engineer - ICT | 12.00 | Month |  | 1500000.00 | 18000000.00 | 18000000.00 | SYSTRA MVA Consulting (India) Private Limited
4.31 | Senior Engineer - Airport System, | 12.00 | Month |  | 1500000.00 | 18000000.00 | 18000000.00 | SYSTRA MVA Consulting (India) Private Limited
5.00 | Part D - Supervision staff during DLP stage
5.01 | Civil Engineer | 84.00 | Month |  | 575000.00 | 48300000.00 | 48300000.00 | SYSTRA MVA Consulting (India) Private Limited
5.02 | Electrical Engineer | 84.00 | Month |  | 575000.00 | 48300000.00 | 48300000.00 | SYSTRA MVA Consulting (India) Private Limited
6.00 | 1. Payment of PMC Fee 1.1 The PMC fee shall comprise of following Components i) Part A - Design & Pre-Construction Stage upto award of EPC contracts and Services during execution stage ii) Part B - Miscellaneous Expenditure iii) Part C - Supervision staff during Execution stage iv) Part D - Supervision staff during DLP stage a) Payment shall be made as below:
7.00 | Part A - Design & Pre-Construction Stage upto award of EPC contracts and Services during execution stage: The Consultant is required to quote one lump-sum fee for the entire scope of services, which covers , Design & Pre-Construction Stage (until award of EPC contract), and Services During Execution Stage. This lump-sum fee will be paid in two parts: 1. 60% Payment – Up to Award of EPC Contract All activities related to design, drawings, DPR, tender assistance, bid evaluation, and support until the EPC contract is awarded fall under this stage. For completing this entire pre-construction work, the Consultant will receive 60% of the total quoted fee. 2. 40% Payment – During Construction The remaining 40% of the fee will be paid pro-rata, i.e., in proportion to the financial progress of the EPC contractor during the execution period. As the EPC contractor achieves financial milestones (for example, 10%, 20%, 50% project progress), the Consultant will be paid the corresponding percentage of this 40%. Mobilization and Tools & Plants advance shall not be accounted for financial progress.
8.00 | Part -A Design & Pre-Construction Stage upto award of EPC contracts and Services during execution stage Payment shall be as below: 1. Inception Report : 05% x Quoted Fees of Part A 2. Concept Report : 05% x Quoted Fees of Part A 3. Schematic Design Report : 10% x Quoted Fees of Part A 4. Preliminary Design / Drawings / Technical Specification : 10% x Quoted Fees of Part A 5. Cost Estimate Report :10% x Quoted Fees of Part A 6. Bid Process Management Process – Submission of tender document containing conditions of contract, special conditions of contract, detailed specifications, BOQ, tender drawings & approval by AAI: 10% x Quoted Fees of Part A 7. Bid Evaluation and Award of work :10% x Quoted Fees of Part A 8. Services during execution stage on Pro-rata basis based on financial progress of EPC contract till completion of EPC contract : 40% x Quoted Fees of Part A Note: a) AAI shall pay PMC 80% of the Fee for each stage mentioned above (stage 1 to stage 7) on submission of deliverables within 7 working days and balance 20% within 14 working days after satisfactory incorporation of observation raised by AAI, if any.
9.00 | Part B - Miscellaneous Expenditure The payment under this head shall commence from the date on which the PMC establishes a fully functional site office. The site office shall be equipped with all facilities, infrastructure, furniture, equipment, communication systems, Site Transportation System and staffing. A certificate confirming the establishment and functionality of the site office shall be issued by the Engineer-in-Charge, based on physical verification. The PMC shall maintain the site office in functional condition throughout the duration of the contract. Any interruption, non-availability, or partial functioning of the site office attributable to the PMC shall proportionately affect the payment under this head, as determined by the Engineer-in-Charge. The payment shall be subject to periodic review, and the Engineer-in-Charge may withhold or adjust payment if the site office fails to meet the prescribed standards at any stage. Payment during extended period of EPC contract- In case the period of completion of EPC contract is extended beyond 44 months, Monthly payment towards fixed establishment cost shall continued to be paid. Further, no such payment shall be made for defects liability period. In defects liability period office accommodation shall be provided by AAI and Indian Navy (IN) for their respective areas. Water and electricity charges shall also be borne by AAI and Indian Navy (IN) for their respective areas. The cost of Vehicle for site inspection, Computer, stationary shall be borne by PMC.
10.00 | Part C - Supervision staff during Execution stage: I ) Finalization of Yearly Work Programme At the time of award of work, AAI, the PMC, and the EPC contractor will jointly prepare a yearly work programme, for the first Financial year ending on 31st March. This programme will include monthly financial targets for each month in that particular financial year. Subsequently, work programme for next financial year commencing from 1st April to 31st March financial target shall be fixed and so on. Monthly Payment to PMC i. 80% Payment – Based on Actual Deployment 80% of the man-month fee will be paid every month based strictly on actual deployment of personnel by the PMC. This amount is paid regardless of project financial progress. ii. 20% Payment – Based on achieving Monthly Financial Targets: The remaining 20% of the man-month fee is performance-linked and will be paid only if the monthly financial target (as per the jointly approved programme) is achieved. Mobilization and Tools & Plants advance shall not be accounted for financial progress. Annual Condition In the event that the Annual Financial Target is not achieved by the end of the relevant Financial Year, the 20% Performance-Linked Component shall be recalculated strictly on a pro rata basis, corresponding to the ratio of Actual Achievement to the Annual Financial Target. Payment of the Performance-Linked Component shall be limited to such recalculated amount only. Any shortfall between the Annual Financial Target and the Actual Achievement shall result in a proportionate reduction of the Performance-Linked Component. The amount attributable to such shortfall shall not be payable to the PMC under any circumstances. The PMC expressly acknowledges and agrees that it shall have no right, claim, or entitlement whatsoever to the unreleased portion of the Performance-Linked Component, and the same shall be deemed a permanent and irrevocable deduction. Mobilization and Tools & Plants advance shall not be accounted for financial progress
11.00 | Part D - Supervision staff during DLP stage Payment to the Consultant during the DLP period shall be calculated on a monthly basis, corresponding to the actual deployment of personnel in accordance with the Contract.
12.00 | Note 1: Payment Limitation for Part-A (Design & Pre-Construction Stage) 1. The fee quoted by the PMC for Part-A (Design & Pre-Construction Stage up to award of EPC Contracts and services during execution stage) shall not exceed twenty-five percent (25%) of the total consultancy fees quoted for Part-A, Part-B, Part-C and Part-D combined 2. In the event the PMC quotes a fee for Part-A exceeding twenty-five percent (25%) of the total consultancy fees, the payment for Part-A(1) – Services up to Award of EPC Contract shall be restricted to sixty percent (60%) of twenty-five percent (25%) of the total consultancy fees quoted for Part-A, Part-B, Part-C and Part-D combined or sixty percent (60%) of the quoted fees for Part-A, whichever is minimum. 3. The balance amount of the fee under Part-A, shall not be payable prior to the commencement of construction works and shall be released only under Part-A(2) – Services During Construction, on a pro-rata basis in proportion to the financial progress achieved by the EPC Contractor during the execution period, as certified by the AAI. 4. The PMC shall not be entitled to claim any additional payment for services under Part-A(1) beyond the limit specified above, notwithstanding the fee quoted in its financial proposal. Note 2: In case period of deployment of any personnel is less than one month, payment shall be made on pro-rata basis of man-month quote. b) Escalation: Escalation shall be paid @ of 5% per annum (without compounding effect) calculated from the last date of submission of bid, during the stipulated period of the contract including the justified period extended under the provisions of Clause 11 -Extension of Time of General Conditions of Contracts without any action under Clause 8 -Compensation for delay of Special Conditions of Contract. No escalation payment shall be payable for Part-A- Design & Pre-Construction Stage up to award of EPC contracts and Services during execution stage.
| Total in Figures |  |  |  |  | 2970000001.00
Lowest Amount Quoted BY: SYSTRA MVA Consulting (India) Private Limited(2970000001.00)

## BOQ Summary
BOQ Summary Details Tender Title: Project Management Consultancy Services for Development of Greenfield Airport at Great Nicobar Island (GNI), Andaman and Nicobar Islands Tender ID: 2025_AAI_251685_2
Sheet Name | Sl.No | Bidder Name | Amount | Bid Rank
BoQ1 | 1 | SYSTRA MVA Consulting (India) Private Limited (BID ID -1008253) | 2970000001.00 | L1