Scheduled

Schedule-A

(See Clauses 2.1 and 8.1)

# Site of the Project

- The Site

- Site of the Four-Lane with paved shoulder Project Highway shall include the land, buildings, structures and road works as described in Annex-I of this Schedule-A.

- The dates of handing over the Right of Way to the Contractor are specified in Annex-II of this Schedule-A.

- An inventory of the Site including the land, buildings, structures, road works, trees and any other immovable property on, or attached to, the Site shall be prepared jointly by the Authority Representative and the Contractor, and such inventory shall form part of the memorandum referred to in Clause 8.2 (i) of this Agreement.

- The alignment plans of the Project Highway are specified in Annex-III. In the case of sections where no modification in the existing alignment of the Project Highway is contemplated, the alignment plan has not been provided. Alignment plans have only been given for sections where the existing alignment is proposed to be upgraded. The proposed profile of the Project Highways shall be followed by the contractor with minimum FRL as indicated in the alignment plan. The Contractor, however, improve/upgrade the Road Profile as indicated in Annex-III based on site/design requirement.

- The status of the environment clearances obtained or awaited is given in Annex-IV.

Annex – I

(Schedule - A)

[Note: Through suitable drawings and description in words, the land, buildings, structures and road works comprising the Site shall be specified briefly but precisely in this Annex-I. All the chainages/ location referred to in Annex-I to Schedule-A shall be existing chainages.]

### Site

The Site of the Four –Lane Road Project Highway comprises the section of National Highway 53 commencing from Ch.281.600 to 307.600 i.e. on the Raipur-Durg 4-Lane  Road section in the State of Chhattisgarh.

***The land, carriageway and structures comprising the Site are described below.

### Land

The Site of the Project Highway comprises the land (sum total of land already in possession and land to be possessed) as described below:

| Sr. No. | Chainage |  | ROW (m) | Remarks |
| --- | --- | --- | --- | --- |
|  | From | To |  |  |
| 1 | Ch.281.600 | 307.600 | 40.95m and 36.60 m | 19.00km Excluding grad sepretar and other DLP portion |

### Major Bridges

The Site includes the following Major Bridges:-Kharun River

| S. No. | Chainage(km) | Type of Structure |  |  | No.of Spans with span length (m) | Width(m) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Foundation | Sub-structure | Super-structure |  |  |
| 1 | 283.400 to 283.600 | Open Foundation | Wall type Concrete Pier | Rcc Solid Slab | 9 Span,22.22m RHS | 10m |
| 2 | 283.400 to 283.600 | Open Foundation | Wall type Concrete Pier | Rcc Solid Slab | 11Span,18.18 m LHS | 10m |

### Road over-bridges (ROB)/ Road under-bridges(RUB) - RUB

The Site includes the following ROB (road over railway line)/RUB (road under railway line):

| S. No. |  | Chainage (km) | Type of Structure |  |  |  | No. of Spans with span length (m) |  | Width (m) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Foundation | Superstructure |  |  |  |  |  |  |
| 1 | Ch.298.500 |  | Open Foundation |  | Wall type Concrete Pier | Rcc Solid Slab |  | Single Spon 8.5 m |  | 20.50 m |

### Grade separators :-

### The Site includes the following grade separators:

| S. No. | Chainage (km) | Type of Structure |  | No. of Spans with span length (m) | Width (m) | Remark |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Foundation | Superstructure |  |  |  |
| 11111111 | 2862222286.400 | pile foundation | PSC Girder and RCC slab | 11111111000 m | 111111118.50 m | Kumhari |
| 11111112 | 2862222299.00 | Pile foundation | PSC Girder and RCC slab | 11111111000 m | 111111118.50 m | Transport Nagar |
| 11111113 | 3 302.00 | Pile foundation | PSC Girder and RCC slab | 11111111860m m | 111111118.50 m | Power House |
| 4 | 304.00 to 305.00 | Pile foundation | PSC Girder and RCC slab | 11111112190 m | 18.50 m | Supela |

### Minor bridges :-  1 nos. Kosanala

### The Site includes the following minor bridges:

| S. No. | Chainage (km) | Type of Structure |  |  | No. of Spans with span length (m) | Width (m) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Foundation | Sub- structure | Super- structure |  |  |
| 1 | Km.305.960 to km.306.00 (RHS) | Open Foundation | Wall Type,RCC,Concrete | Rcc Solid Slab | 2span 20m=40 m | 10.0m |
| 2 | Km.305.960 to 306.00 (LHS) | Open Foundation | Wall Type,Rcc,Concrete | PSC Girder &Rcc Solid Slab | Single spon 40 m | 10.0m |

### Railway level crossings :-

The Site includes the following railway level crossings:

| S. No. | Location (km) | Remarks |
| --- | --- | --- |
| NIL |  |  |

9.    Under passess(vehicular, non vehicular)

The Site includes the following underpasses:

| S. | Chainage (km) | Type of Structure | No. of Spans with span length (m) | Width (m) |
| --- | --- | --- | --- | --- |
| NIL |  |  |  |  |

#### 10.   Culverts

The Site has the following culverts:

| S. No. | N.H. No. | Location of Bridge / Culvert | Details of Major/Minor/Culvert with span arrangements | Width of Bridge |
| --- | --- | --- | --- | --- |
| 1 | 53 | 282.300 | 3.50m CULVERT | 40.95m |
| 2 | 53 | 283.400 | H.L. Bridge 9m span of 20m | 2x10.00m |
| 3 | 53 | 284.600 | 1m H.P. CULVERT | 36.60m |
| 4 | 53 53 | 287.600 | 1m H.P. CULVERT | 40.95m |
| 5 |  | 287.10B | 2.00m | 40.95m |
| 6 | 53 | 288.600A | 3.00 | 40.95m |
| 7 | 53 | 289.400 | S.S.A. 2X3(1.30/2X0.70) Irrigation may widerd with H.P. 1M DIA. BOTH SIDE AND SINGLE PIPE | 40.95m |
| 8 | 53 | 290.400 | 6.00M | 40.95m |
| 9 | 53 | 291.200 | 6.00M | 40.95m |
| 10 | 53 | 291.400 | H.P. CULVERT ONE ROW 1M DIA. | 40.95m |
| 11 | 53 | 292.600 | RCC SLAB CULVERT ONE SPAN OF 2 M | 36.60m |
| 12 | 53 | 293.800 | RCC SLAB CULVERT ONE SPAN OF 2 M | 36.60m |
| 13 | 53 | 294.600 | ONE SPAN OF 3M RCC SLAB | 36.60m |
| 14 | 53 | 295.400 | ONE SPAN OF 5M RCC SLAB | 36.60m |

| 15 | 53 | 296.600 | 3 SPAN RCC CULVERT | 36.60m |
| --- | --- | --- | --- | --- |
| 16 | 53 | 298.000 | 1 ROW 1MT. DIA HP. CULVRT | 36.60m |
| 17 | 53 | 299.200 | RCC SLAB 3M SPAN | 40.95m |
| 18 | 53 | 298.600 | RCC SLAB 1X 7.10X6.00 | 40.95m |
| 19 | 53 | 298.900 | RCC SLAB 3M 4.50X2.275M | 40.95m |
| 20 | 53 | 301.000 | 1 SPAN OF 3M STONE ARCH WIDEND(L/S+R/S) 2.5M BOTH SIDE WITH RCC SLAB | 40.95m |
| 21 | 53 | 301.800 | HP 1M DIA. | 40.95m |
| 22 | 53 | 306.200 | H.L. Bridge 2 span of 20 m | 40.95m |
| 23 | 53 | 306.600 | RCC SLAB CULVERT 5 M | 40.95m |

### 11.      Busbays :-The details of bus bays on the Site are as follows:

| S. No. | Chainage (km) | Length (m) | Left Hand Side | Right Hand Side |
| --- | --- | --- | --- | --- |
| NIL |  |  |  |  |

### 12.      Truck Laybyes :-The details of truck lay byes are as follows:

| S. No. | Chainage (km) | Length (m) | Left Hand Side | Right Hand Side |
| --- | --- | --- | --- | --- |
| NIL |  |  |  |  |

#### 13.             Road side drains

The details of the roadside drains are as follows:

| S. No. | Location |  | Type |  |
| --- | --- | --- | --- | --- |
|  | From km | to km | Masonry/cc (Pucca) | Earthen (Kutcha) |
| 1 | km 281.600 | 283.100 | cc | - |
| 2 | km 284.00 | 287.000 | cc | - |
| 3 | km 290.80 | 298.100 | cc | - |
| 4 | km 299.00 | 307.00 | cc | - |

#### 14.   Major  junctions

The details of major junctions are as follows:

| S. No. | Location |  | At grade | Separated | Category of Cross Road |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | From km | to km |  |  | NH | SH | MDR | Others |
| 1 | 286.400 | 286.440 | Yes | - | - | yes | - | - |
| 2 | 295.700 | 295.740 | Yes | - | - | - | - | yes |
| 3 | 298.900 | 298.935 | Yes | - | - | - | - | yes |
| 4 | 300.400 | 300.440 | Yes | - | - | - | - | yes |
| 5 | 301.900 | 302.000 | Yes | - | - | - | yes | - |
| 6 | 304.000 | 304.018 | Yes | - | - | - | - | yes |
| 7 | 304.900 | 304.940 | Yes | - | - | - | - | yes |
| 8 | 307.500 | 307.550 | Yes | - | - | - | - | yes |

(NH: National Highway, SH: State Highway, MDR: Major District Road)Major junctions:-

### 15.          Minor Junctions:-Nos.

The details of the minor junctions are as follows:

| S.No. | Location | Type |
| --- | --- | --- |
| 1 | 282.900 | T-Junction (Middle Cut) |
| 2 | 290.00 | Middle-Cut |
| 3 | 292.500 | Middle-Cut |
| 4 | 293.400 | Middle-Cut |
| 5 | 296.700 | Middle -Cut |

### 16.       Bypasses :-

The details of the existing road sections proposed to be bypassed are as follows:

| S. No. | Name of bypass (town) | Chainage (km) From km to km | Length (in Km) |
| --- | --- | --- | --- |
| NIL |  |  |  |

### 17.      Other Structures :-  NIL

| S. No. | Location | Type |
| --- | --- | --- |
| NIL |  |  |

Annex – II

#### Annex – II

(As per Clause 8.3 (i))

##### (Schedule-A)

Dates for providing Right of Way of Construction Zone

The dates on which the Authority shall provide Right of Way of Construction Zone to the Contractor on different stretches of the Site are stated below:

| Sl. No | From km to km | Length (km) | Width (m) | Date of providing Right of Way* |
| --- | --- | --- | --- | --- |
| (1) | (2) | (3) | (4) | (5) |
| (i) Full Right of Way (full width) - Stretch - Stretch | km 281.600 to km 307.600 | 19.00 | 40.95 & 36.60 | Between Both Side Shoulder MainLane and Service Lane For Rcc Crash Barrier At the time of Date of Appointment |
| (c) Stretch |  |  |  |  |
| (ii) Part Right of Way (part width) - Stretch - Stretch - Stretch | nil |  |  |  |
| (iii) Balance Right of Way (width) - Stretch - Stretch - Stretch | nil |  |  |  |

*The dates specified herein shall in no case be beyond 150 (one hundred and fifty) day after the Appointed Date.

Annex - III (Schedule-A) Alignment Plans

The existing alignment of the Project Highway shall be modified as per the alignment plan indicated below:

- The alignment of the Project Highway is enclosed in alignment plan. Finished road level indicated in the alignment plan shall be followed by the contractor as minimum FRL. In any case, the finished road level of the project highway shall not be less than those indicated in the alignment plan. The contractor shall, however, improve/upgrade the Road profile as indicated in Annex-III based on site/design requirement.

- Traffic Signage plan of the Project Highway showing numbers & location of traffic signs is enclosed. The contractor shall, however, improve/upgrade upon the traffic signage plan as indicated in Annex-III based on site/design requirement as per the relevant specifications/ IRC Codes /Manual.

Alignment Plan;-

- Existing Road FRL to be followed.

Annex – IV (Schedule-A)

### Environment Clearances

The following environment clearances are not required.;- Not Required

| Sr.No |  |  |  |
| --- | --- | --- | --- |
| Not Applicable |  |  |  |

Schedule - B (See Clause 2.1)

# Development of the Project Highway

- Development of the Project Highway

Development of the Project Highway shall include design and construction of the Project Highway as described in this Schedule-B and in Schedule-C. The alignment plans of the Project Highway are specified in Annex-III of Schedule A. The proposed profile of the Project Highway shall be followed by the contractor with minimum FRL as indicated in the alignment plan. The contractor however, improve/upgrade the Road Profile as indicated in Annex-III based on site/design requirement.

- Rehabilitation and augmentation

Rehabilitation and Augmentation shall include Construction of RCC Crash Barrier Between Main Carriageway and Service Road in  Km.281.600 To Km. 307.600 of N.H. 53 (Old N.H.06) In Chhattisgarh State Under Road Safety Work as described in Annex-I of this Schedule-B and in Schedule-C.

- Specifications and Standards

The Project Highway shall be designed and constructed in conformity with the Specifications and Standards specified in Annex-I of Schedule-D.

Annex-I

(Schedule-B)

### Description of [Four-Laning]

### Widening of the Existing Highway

- Project Highway comprises the section of National Highway 53 commencing from Chainage km 281.600 to km. 307.600 i.e. Raipur-Durg – 4-Lane Road section in the state of Chhattisgarh. Total work  Length of project is 19.00km The Project Highway shall follow the alignment as proposed unless otherwise specified by the Authority and shown in the alignment plans specified in Annex-III of Schedule-A. Geometric deficiencies, if any, in the existing horizontal and vertical profiles shall be corrected as per the prescribed standards for plain/rolling terrain to the extent land is available.

- Work Name  RCC Crash Barrier :-

Construction of RCC Crash Barrier Between Main Carriageway and Service Road in  Km.281.600 To Km. 307.600 of N.H. 53 (Old N.H.06) In Chhattisgarh State Under Road Safety Work along with reconstruction of central median and Painting on RCC crash Barrier.

2               Geometric Design and General Features :

- General :- Geometric design and general features of the Project Highway shall be in accordance with Section 2 of the Manual (IRC:119-2015).

- Design speed :- Nil

- Improvement of the existing road geometrics

In the following sections, where improvement of the existing road geometrics to the prescribed standards is not possible, the existing road geometrics shall be improved to the extent possible within the given right of way and proper road signs and safety measures shall be provided:

| S. No. | Design Chainage | Type of Deficiency | Remarks |
| --- | --- | --- | --- |
| NIL |  |  |  |

- Right of Way :-

Details of the Right of Way are given in Annex II of Schedule-A.

- Type of shoulders. :-NIL

- Lateral and vertical clearances at underpasses:NIL

- Lateral and vertical clearances	at underpasses and provision of guardrails/crash barriers shall be as per the provision of relevant Manual.

- Lateral clearance: The width of the opening at the underpasses shall be as follows:

| S.No. | Location (Chainage) (from km to km) | Span/ opening (m) | Remarks |
| --- | --- | --- | --- |
| NIL. |  |  |  |

- Lateral and vertical clearances at overpasses

- Lateral and vertical clearances at overpasses shall be as per the provision of relevant Manual.

- Lateral clearance: The width of the opening at the overpasses shall be as follows

| S.No. | Location (Chainage) (from km to km) | Span/opening(m) | Remarks |
| --- | --- | --- | --- |
| NIL |  |  |  |

- Service Road.

Service roads shall be constructed at the locations and for the lengths indicated below:

| Sl. No. | Location of service road (from km to km) | Right hand side(RHS)/Left hand side (LHS)/ or Both sides | Length (m) of Service Road |
| --- | --- | --- | --- |
|  |  | NIL |  |

- Grade separated structures :-

- Grade separated structures shall be provided as per provision of the relevant Manual. The requisite particulars are given below:

| S.No. | Location of Structure | Length (m) | Number and Length of Spans | Approach Gradient | Remarks if any |
| --- | --- | --- | --- | --- | --- |
| NIL |  |  |  |  |  |

- In the case of grade separated structures, the type of structure and the level of the Project Highway and the cross roads shall be as follows:

| S.No. | Location | Type of Structure and Length (m) | Cross Road at |  |  | Remarks if any |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Existing Level | Raised Level | Lowered Level |  |
| NIL |  |  |  |  |  |  |

- Cattle and pedestrian underpass/overpass :-

Cattle and pedestrian underpass/ overpass shall be constructed as follows:

| S.No. | Location | Type of Crossing |
| --- | --- | --- |
| NIL |  |  |

Typical cross-sections of the Project Highway:

- TCS-I Main Lane and Service Lane between construction of RCC Crash Barrier from km.281.600 to 307.600 OF Road BHS (LHS+RHS)

| TCS-I |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TCS-II |  |  |  |  |  |  |  |  |

NIL

Note:

- Adequate facilities to be provided for ingress and egress of service road and main carriageway for which no positive Change of Scope will be eligble.

### Intersections and Grade Separators:- NIL

All intersections and grade separators shall be as per the provision of the Manual. Existing intersections which are deficient shall be improved to the prescribed standards.

Properly designed intersections shall be provided at the locations and of the types and features given in the tables below:

- At-grade intersection:- As per IRC:SP:84-2019

| Sl. No. | Location of intersection | Type of intersection | Other features |
| --- | --- | --- | --- |
| NIL |  |  |  |

- Grade separated intersection with/without ramps.

| Sl. No. | - Location | - Salient features | - Minimum length of viaduct to be provided | - Road to be carried over/under the structures |
| --- | --- | --- | --- | --- |
| NIL |  |  |  |  |

Rumble strips: The cross road junction shall be provided with rumble strips on NH and speed breaker on cross road at junction.

### Dismantling work for improvement of exiting road.. NIL

### Pavement Design.

- Pavement design shall be carried out in accordance with the provision of the Manual.

- Type of pavement:-Nil

- Design requirements

  - Design Period and strategy Nil

  - Design Traffic Nil

- Re-construction of stretches.

The following stretches of the existing road shall be reconstructed. These shall be designed as new pavement.

| Sl.No. | Stretch From km to km | Remarks |
| --- | --- | --- |
| Nil |  |  |

### Road side Drainage

Drainage system including surface and subsurface drains for the Project Highway shall be provided as per the provision of the Manual.

RCC covered drain of minimum inner dimensions of 1mx1m shall be provided at following locations:

| S.No. | Design Chainage | RHS/ LHS/ Both sides | Length (m) | Remark |
| --- | --- | --- | --- | --- |
| Nil |  |  |  |  |

### Design of Structures.

- General

  - All bridges, culverts and structures shall be designed and constructed in accordance with the provision of the Manual for a minimum design life period of 100 years and shall conform to the cross- sectional features and other details specified therein.

  - Width of the carriageway of new bridges and structures shall be as follow:

Nil

  - The following structures shall be provided with footpaths:

[Refer to the provision of relevant Manual and provide details of new Structures with footpath.]

| S. No. | Location at km | Remarks |
| --- | --- | --- |
| Nil |  |  |

  - All bridges shall be high-level bridges.

  - The following structures shall be designed to carry utility services specified in  table below:

| S. No. | Bridge at km | Utility service to be carried | Remarks |
| --- | --- | --- | --- |
| Nil |  |  |  |

(f)       Cross-section of the new culverts and bridges at deck level for the Project Highway shall conform to the typical cross-sections given in the provision of the Manual.

- Culverts.

  - Overall width of all culverts shall be equal to the roadway width of the approaches.

  - Reconstruction of existing culverts:

The existing culverts at the following locations shall be re-constructed as new culverts:

| Sl. No. | Culvert location | Span/Opening (m) | Remarks, if any* |
| --- | --- | --- | --- |
| NIL |  |  |  |

*[Specify modifications, if any, required in the road level, etc.]

  - Widening of existing culverts:

All existing culverts which are not to be reconstructed shall be widened tothe roadway width of the Project Highway as per the typical cross section given in the provision of relevant Manual. Repairs and strengthening of existing structures where required shall be carried out.

| S. No. | Culvert location | Type, span, height and width of existing culvert (m) | Repairs to be carried out [specify] |
| --- | --- | --- | --- |
| NIL |  |  |  |

  - New culverts shall be constructed as per particulars given in the table below:

| S. No. | Culvert location | Type, span, height and width of existing culvert (m) | Repairs to be carried out [specify] |
| --- | --- | --- | --- |
| NIL |  |  |  |

  - Repair/Replacement of railing/parapets, flooring and protection works of the existing culverts shall be undertaken as follows:-

| S.No. | Location | Type of repairs required |
| --- | --- | --- |
| NIL |  |  |

  - Floor protection works shall be as specified in the relevant IRC Codes and Specification.

- Bridges.

  - Existing bridges to be re-constructed/widened

(i) The existing bridges at the following locations shall be re-constructed as new Structures.

| Sr. No | Bridge Location (km) | Salient details of existing Bridge | Adequacy or otherwise of the existing waterway, vertical clearance etc. | Remarks |
| --- | --- | --- | --- | --- |
| NIL |  |  |  |  |

(ii)	The following narrow bridges shall be widened:

| Sl. No. | Location (km) | Existing width (m) | Extent of widening (m) | Cross-section at deck level for widening @Attached cross section |
| --- | --- | --- | --- | --- |
| NIL |  |  |  |  |

  - Additional new bridges

New bridges at the following locations on the Project Highway shall be constructed.

| Sl. No. | Location (km) | Total length (m) | Remarks, if any |
| --- | --- | --- | --- |

Note:- Tentative GADs for the new bridges are attached in the drawings folder

  - The railings of existing bridges shall be replaced by crash barriers at the following locations:

| Sl.No. | Location at km | Remarks |
| --- | --- | --- |
| Nil |  |  |

  - Repairs/replacements of railing/parapets of the existing bridges shall be undertaken as follows:

| Sl. No. | Location at km | Remarks |
| --- | --- | --- |

  - Drainage system for bridge decks :-

An effective drainage system for bridge decks shall be provided as specified in the provision of relevant Manual.

  - Structures in marine environment:-NIL

- Rail-road bridges: Nil

  - Design, construction and detailing of ROB/RUB shall be as specified in the provision of relevant Manual. [Refer to the provision of relevant Manual and specify modification, if any]

(b) 	Road over-bridges

Road over-bridges (road over rail) shall be provided at the following level crossings, as per GAD drawings attached:

| Sl. No. | Location of Level crossing (Existing km) | Design Chainage of proposed ROB | Length |
| --- | --- | --- | --- |
| NIL |  |  |  |

(c)	Road under-bridges

Road under-bridges (road under railway line) shall be provided at the following level crossings, as per GAD drawings attached:

| Sl. No. | Location of Level crossing (Chainage ) | Number and length of span (m) |
| --- | --- | --- |
| NIL |  |  |

- Grade separated structures : Nil

The grade separated structures shall be provided at the locations and of the type and length specified in paragraphs 2 (ix) and 3 of this Annex-I.

- Repairs and strengthening of bridges and structures

The existing bridges and structures to be repaired/strengthened, and the nature and extent of repairs /strengthening required are given below:

  - Bridges –

| Sl. No. | Location of bridge (km) | Nature and extent of repairs/strengthening to be carried out |
| --- | --- | --- |

  - ROB /RUB

| Sr.No. |  | Location of bridge (km) | Nature and extent of repairs/strengthening to be carried out |
| --- | --- | --- | --- |
| NIL |  |  |

  - Overpasses/Underpasses and other structures

| Sl. No. | Location of Structure (km) | Nature and extent of repairs /strengthening to be carried out |
| --- | --- | --- |
| NIL |  |  |

- List of Major Bridges and Structures Retained: NIL

The following is the list of the Major Bridges and Structures:

| Sr. No | Design Chainage (km) | Span Arrangement | Type of Structure | Remarks. |
| --- | --- | --- | --- | --- |
| NIL |  |  |  |  |

Note;- "Minimum 25%of total concrete volume other than the foundations & sub-structures of Bridges/ Viaduct/RoB for new construction, reconstruction and widening shall be mandatorily factory manufactured pre-cast concrete elements, if such factory is there within 100 km distance from any point on the project. Any relaxation to the use of factory manufactured pre-cast concrete elements may be granted by Authority only if the contractor/ concessionaire is able to demonstrate that the manufacturer(s) is not able to provide such products matching to the works programme of the contractor or the prices of such products demanded by the manufacturer for onsite delivery is more than the prices derived for corresponding cast-in-situ item at the SoR rates prevailing on 28th day before the Bid Due Date."

### Traffic Control Devices and Road Safety Works:

- Construction of Concrete Crash Barrier: Concrete Crash Barrier to be constructed between Main Carriageway and Service Road as per IRC Specifications at following location:

| S. No. | From | To | Side | Unit | Length | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 281+600 | 307+600 | BHS | RM | 38000 | RCC Crash Barrier New work |

- Reconstruction of Concrete Crash Barrier: Existing Concrete Crash Barrier to be maintained as per standards and specifications at following location:

| S. No. | From | To | Side | Unit | Length | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 297+400 | 297+420 | BHS | Rm | 40 | Reconstruction of existing crash barrier at median |
| 2 | 297+945 | 297+955 | BHS | Rm | 20 | Reconstruction of existing crash barrier at median |
| 3 | 300+845 | 300+855 | BHS | Rm | 20 | Reconstruction of existing crash barrier at median |
| 4 | 301+005 | 301+015 | BHS | Rm | 20 | Reconstruction of existing crash barrier at median |
| 5 | 302+720 | 302+800 | BHS | Rm | 160 | Reconstruction of existing crash barrier at median |
| 6 | 303+340 | 303+500 | BHS | Rm | 320 | Reconstruction of existing crash barrier at median |
| 7 | 305+640 | 305+650 | BHS | Rm | 20 | Reconstruction of existing crash barrier at median |
| 8 | 306+600 | 306+550 | BHS | Rm | 100 | Reconstruction of existing crash barrier at median |
| 9 | 289+905 | 290+000 | BHS | Rm | 40 | Reconstruction of existing crash barrier at median |
| 10 | 286+870 | 287+000 | BHS | Rm | 520 | Reconstruction of existing crash barrier at median |
| 11 | 283+050 | 283+150 | RHS | Rm | 400 | Reconstruction of existing crash barrier at median |
| Total |  |  |  |  | 1660 |  |

Note: The above length is tentative and minimum specified. The actual location shall be finalised in consultation with Authority Engineer. Any increase in above length shall not constitute any Change of Scope.

- Painting of Concrete Crash Barrier: Painting of Concrete Crash Barrier to be done as per standards and specifications at following location:

| S. No. | From | To | Side | Unit | No. | Length | Area | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 297+400 | 297+420 | BHS | Sqm | 2 | 20 | 40 | Crash Barrier top To Bottom |
| 2 | 297+945 | 297+955 | BHS | Sqm | 2 | 10 | 20 | Crash Barrier top To Bottom |
| 3 | 300+845 | 300+855 | BHS | Sqm | 2 | 10 | 20 | Crash Barrier top To Bottom |
| 4 | 301+005 | 301+015 | BHS | Sqm | 2 | 10 | 20 | Crash Barrier top To Bottom |
| 5 | 302+720 | 302+800 | BHS | Sqm | 2 | 80 | 160 | Crash Barrier top To Bottom |
| 6 | 303+340 | 303+500 | BHS | Sqm | 2 | 160 | 320 | Crash Barrier top To Bottom |
| 7 | 305+640 | 305+650 | BHS | Sqm | 2 | 10 | 20 | Crash Barrier top To Bottom |
| 8 | 306+600 | 306+550 | BHS | Sqm | 2 | 50 | 100 | Crash Barrier top To Bottom |
| 9 | 289+905 | 290+000 | BHS | Sqm | 2 | 20 | 40 | Crash Barrier top To Bottom |
| 10 | 286+870 | 287+000 | BHS | Sqm | 4 | 130 | 520 | Crash Barrier top To Bottom at Kumhari flyover Durg side |
| 11 | 283+050 | 283+150 | BHS | Sqm | 4 | 100 | 400 | Crash Barrier top To Bottom at Kumhari flyover Durg side |
| 12 | 281+600 | 307+600 | BHS | Sqm | 2 | 19000 | 38000 | Crash Barrier top To Bottom |
| Total |  |  |  |  |  |  | 39660 |  |

### Road side Furniture. Nil

### Compulsory Afforestation:- Nil

### Hazardous Locations

The safety barriers shall be provided at the following hazardous locations:

| Sl.No. | Location stretch from (km)to(km) | LHS/RHS |
| --- | --- | --- |
| NIL |  |  |

### Special Requirement for Hill Roads: NIL

### Change of Scope

The length of Structures and bridges specified herein above shall be treated as an approximate assessment. The actual lengths as required on the basis of detailed investigations shall be determined by the EPC Contractor in accordance with the Specifications and Standards. Any variations in the lengths specified in this Schedule- B shall not constitute a Change of Scope, save and quantity except any variations in the length arising out of a Change of Scope `

(Schedule B-1)

Annexure-II

    - The shifting of utilities shall be carried out by the EPC Contractor. The cost of the same shall be paid to the contractor as per Schedule-H, which includes all incidental charges, GST, Labour charges, overhead charges, transportation cost etc.. The details of utilities are as follows:

| S. No | Type of Utility | Unit | Quantity | Location/stretch (LHS/RHS) |
| --- | --- | --- | --- | --- |
| Nil |  |  |  |  |

SCHEDULE – C

(See Clause 2.1)

PROJECT FACILITIES

- Project Facilities :-

The Contractor shall construct the Project Facilities in accordance with the provisions of this Agreement. Such Project Facilities shall include:

  - roadside furniture;

  - Pedestrian Facilities

  - Tree- Plantation

  - others to be specified

- Description of Project Facilities :-Each of the Project Facilities are briefly described below:

- Road side Furniture shall be provided as follows: -Nil

- Traffic Signs and Pavement Markings

- PCC Kerb with W-beam Metal Crash Barrier

| S. No. | Location stretches (km) | LHS/RHS |
| --- | --- | --- |
| Nil |  |  |

- Traffic Safety Devices in consultation with Authority’s Engineer & as per the provision of the manual .

- Pedestrian Facilities: Nil

The additional pedestrians’ facilities in the form of guard rails, footpath, lighting etc. shall be provided in built-up area and high embankment of structures.

For proper approaches to adjoining agricultural fields along excavated drains, 900 mm dia. NP2 pipes for about 7.5m in length with adequate cushion over pipe at an interval of 500m on both sides & wherever required as per site requirements in consultation with Authority Engineer shall be provided.

- Tree- Plantation Nil

| S. No. | Location stretches (km) | LHS/RHS |
| --- | --- | --- |

- Other to be Specify;- Nil

Highway Lighting:- Lighting shall be at the following location

| S.No. | Location | Side | Description |
| --- | --- | --- | --- |
| Nil |  |  |  |

SCHEDULE – D

(See Clause 2.1)

# SPECIFICATIONS AND STANDARDS

- Construction

The Contractor shall comply with the Specifications and Standards set forth in Annex-I of this Schedule-D for construction of the Project Highway.

- Design Standards

The Project Highway including Project Facilities shall conform to design requirements set out in the following documents:

- MoRTH Specifications for Road and Bridge Works (5th Revision) 2013 with upto dates amendments

- IRC:SP:55-20014 ”Guidelines on Traffic Management in Work Zones”

- IRC:SP:84-2019 “Manual of specifications & Standards for Four Lanning with paved shoulder of Highways’’ and amendment up to Bid date.

- IRC:67-2022  “ Code of Practice for Road Signs”

- IRC:35-2015  “Code of Practice for Road Markings”

- IRC:112-2019 “Code of Practice for Concrete Road Bridges”

- All the IRC Code & manuals and MoRTH Circular and amendments issued by the Ministry upto 60 days prior to Bid due date for execution of NH works will be applicable

- Other relevant codes.IRC:119-2015

Annex - I

(Schedule-D)

## SPECIFICATIONS AND STANDARDS FOR CONSTRUCTION

## 1	Specifications and Standards

All Materials, works and construction operations shall conform to the Manual of Specifications and Standards for Four-Laning with Paved shoulder of Highways IRC:SP:84-2019, referred to as the Manual, and MORTH Specifications for Road and Bridge Works. Where the specification for a work is not given, Good Industry Practice shall be adopted to the satisfaction of the Authority’s Engineer.

## 2	Deviations from the Manual

(i) 	The terms “Concessionaire”, “Independent Engineer” and “Concession Agreement” used in the Manual shall be deemed to be substituted by the terms “Contractor”, “Authority’s Engineer” and “Agreement” respectively.

| S. No. | Refered in the manual | Item | Description of Deviation |
| --- | --- | --- | --- |
| 1 | IRC:119-2015 | IRC:119-2015 | As per TCS-I, (Refer Drawing Volume) |
| 2 | IRC:119-2015 | IRC:119-2015 | As per TCS (Refer Drawing Volume) |

(ii) Notwithstanding anything to the contrary contained in Paragraph 1 above, Manual, the following Specifications and Standards shall apply to the Project Highway, and for purposes of this Agreement, the aforesaid Specifications and Standards shall be deemed to be amended to the extent set forth below:

"Design, fabrication/ casting and launching/installation of factory manufactured. pre-cast concrete elements will be done as per relevant IRC/BIS standards/guidelines/codes duly considering expected handling/lifting stresses. Any international guidelines such as ASHTO, FHWA (Accelerated Bridge Construction. Guidelines), Japan ft Euro codes, may be followed in case of any gaps in IRC/BIS standards/ guidelines/ codes. The pre-cast factory shall have minimum facility of fully automatic RMC plant, arrangement for steam curing, mechanical handling of concrete and pre-cast components, bar bending machines, stacking yard, in-house design team and NABL accredited quality control laboratory, RO plant for water purification, etc. The precast factory shall be certified by Quality Council of India if it is so mandated by MoRTH."

- Structural steel to be used in construction of Belsonda ROB shall be from

Primary sales manufacturers.

Schedule - E

(See Clauses 2.1 and 14.2)

Maintenance Requirements

1. 	Maintenance Requirements

(i) 	The Contractor shall, at all times maintain the Project Highway in accordance with the provisions of this Agreement, Applicable Laws and Applicable Permits.

(ii) 	The Contractor shall repair or rectify any Defect or deficiency set forth in Paragraph 2 of this Schedule-E within the time limit specified therein and any failure in this behalf shall constitute non-fulfilment of the Maintenance obligations by the Contractor.  Upon occurrence of any breach hereunder, the Authority shall be entitled to effect reduction in monthly lump sum payment as set forth in Clause 14.6 of this Agreement, without prejudice to the rights of the Authority under this Agreement, including Termination thereof.

(iii) 	All Materials, works and construction operations shall conform to the MORTH Specifications for Road and Bridge Works, and the relevant IRC publications. Where the specifications for a work are not given, Good Industry Practice shall be adopted.

2. 	Repair/rectification of Defects and deficiencies

The obligations of the Contractor in respect of Maintenance Requirements shall include repair and rectification of the Defects and deficiencies specified in Annex - I of this Schedule-E within the time limit set forth therein.

3.	Other Defects and deficiencies

In respect of any Defect or deficiency not specified in Annex - I of this Schedule-E, the Authority’s Engineer may, in conformity with Good Industry Practice, specify the permissible limit of deviation or deterioration with reference to the Specifications and Standards, and any deviation or deterioration beyond the permissible limit shall be repaired or rectified by the Contractor within the time limit specified by the Authority’s Engineer.

4. 	Extension of time limit

Notwithstanding anything to the contrary specified in this Schedule-E, if the nature and extent of any Defect or deficiency justifies more time for its repair or rectification than the time specified herein, the Contractor shall be entitled to additional time in conformity with Good Industry Practice. Such additional time shall be determined by the Authority’s Engineer and conveyed to the Contractor and the Authority with reasons thereof.

5. 	Emergency repairs/restoration

Notwithstanding anything to the contrary contained in this Schedule-E, if any Defect, deficiency or deterioration in the Project Highway poses a hazard to safety or risk of 	damage to property, the Contractor shall promptly take all reasonable measures for eliminating or minimizing such danger.

6. 	Daily inspection by the Contractor

The Contractor shall, through its engineer, undertake a daily visual inspection of the Project Highway and maintain a record thereof in a register to be kept in such form and manner as the Authority’s Engineer may specify. Such record shall be kept in safe custody of the Contractor and shall be open to inspection by the Authority and the Authority’s Engineer at any time during office hours.

7. 	Pre-monsoon inspection / Post-monsoon inspection

The Contractor shall carry out a detailed pre-monsoon inspection of all bridges, culverts and drainage system before [1st June] every year in accordance with the guidelines contained in IRC: SP35. Report of this inspection together with details of proposed maintenance works as required on the basis of this inspection shall be sent to the Authority’s Engineer before the [10th June] every year. The Contractor shall complete the required repairs before the onset of the monsoon and send to the Authority’s Engineer a compliance report. Post monsoon inspection shall be done by the [30th September] and the inspection report together with details of any damages observed and proposed action to remedy the same shall be sent to the Authority’s Engineer.

8. 	Repairs on account of natural calamities

All damages occurring to the Project Highway on account of a Force Majeure Event or wilful default or neglect of the Authority shall be undertaken by the Authority at its own cost. The Authority may instruct the Contractor to undertake the repairs at the rates agreed between the Parties.

Annex - I

(Schedule-E)

Repair/rectification of Defects and deficiencies

The Contractor shall repair and rectify the Defects and deficiencies specified in this Annex-I of Schedule-E within the time limit set forth in the table below.

Table -1: Maintenance Criteria for Pavements:

| Asset Type | Annex – I Performance Parameter | Level of Service (LOS) |  | Frequency of Inspection | Tools/ Equipment |  | Standards and References for Inspection and Data Analysis | Time limit for Rectification/ Repair | Maintenance Specifications |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Desirable | Acceptable |  |  |  |  |  |  |
| Flexible pavement (Pavement of MCW, Service Road, approach | Potholes | Nil | <0.1%ofareaandsubject to limit of10 mm indepth | Daily |  | Length Measurement Unit like Scale, Tape, odometer etc. | IRC 82: 2015 and Distress Identification Manual for Long Term Pavement Performance Program, FHWA 2003 (http://www.tfhrc.com/pavement/ lttp/reports/03031/) | 24-48 hours | MORT&H Specification 3004.2 |

| Asset Type |  | Performance Parameter |  | Level of Service |  |  |  | Frequency of Inspection |  | Tools/ Equipment |  | Standards and References forInspection and Data Analysis |  | Time limit for Rectification/ Repair |  | Maintenance Specifications |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Desirable |  | Acceptable |  |  |  |  |  |  |  |  |  |  |  |
| Gradestructure, approaches of connecting roads, sliproads, lay byes etc.as applicable | Cracking |  | Nil |  | < 5 % subject tolimit of0.5 sqm for any50 mlength |  | Daily |  | Length Measurement Unit likeScale, Tape, Odometeretc. |  |  |  | 7-15 days |  | MORT&H Specification 3004.3 |  |
|  | Rutting |  | Nil |  | < 5 mm |  | Daily |  | Straight Edge |  |  |  | 15 -30 days |  | MORT&H Specification 3004.3 |  |
|  | Corrugations and Shoving |  | Nil |  | < 0.1 % of area |  | Daily |  | Length Measurement Unit like |  |  |  | 2-7 days |  | IRC:82- 2015 |  |
|  | Bleeding |  | Nil |  | < 1 % of area |  | Daily |  | Scale, Tape, odometer etc. |  |  |  | 3-7 days |  | MORT&H Specification 3004.4 |  |
|  | Raveling/ Stripping |  | Nil |  | < 1 % of area |  | Daily |  |  |  |  |  | 7-15 days |  | IRC:82- 2015 read with IRC SP 81 |  |
|  | Edge Deformation/ Breaking |  | Nil |  | <1 m for any 100 m section and width < 0.1 m at any location, restricted to 30cm from the edge |  | Daily |  |  |  |  |  | 7- 15 days |  | IRC:82- 2015 |  |

| Asset Type | Performance Parameter | Level of Service |  | Frequency of Inspection | Tools/ Equipment | Standards and References forInspection and Data Analysis | Time limit for Rectification/ Repair | Maintenance Specifications |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Desirable | Acceptable |  |  |  |  |  |
|  | Roughness BI | 2000 mm/km | 2400 mm/km | Bi-Annually | Class I Profilometer SCRIM (Side way force Coefficient Routine Investigation Machine or equivalent) | Class I Profilometer : ASTM E950 (98) :2004 –Standard Test Method for measuring Longitudinal Profile of Travelled Surfaces with Accelerometer Established Inertial Profiling Reference ASTM E1656 -94: 2000- Standard Guide for Classification of Automatic Pavement Condition Survey Equipment | 180 days | IRC:82- 2015 |
|  | Skid Number | 60SN | 50SN | Bi-Annually |  |  | 180 days | BS:7941-1: 2006 |
|  | Pavement Condition Index | 3 | 2.1 | Bi-Annually |  |  | 180 days | IRC:82- 2015 |
|  | Other Pavement Distresses |  |  | Bi-Annually |  |  | 2-7 days | IRC:82- 2015 |
|  | Deflection/ Remaining Life |  |  | Annually | Falling Weight Deflectometer | IRC 115: 2014 | 180 days | IRC:115- 2014 |

| Asset Type | Performance Parameter | Level of Service |  |  | Frequency of Inspection | Tools/ Equipment | Standards and References for Inspection and Data Analysis | Time limit for Rectification/ Repair | Maintenance Specifications |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Desirable | Acceptable |  |  |  |  |  |  |
| Rigid Pavement (Pavement of MCW, Service Road, Grade structure,approaches of connecting roads,slip roads, laybyes etc.as applicable | Roughness BI | 2200m m/km | 2400mm /km |  | Bi-Annually | Class-I Profilometer | ASTM E950 (98) :2004 and ASTM E1656 -94: 2000 | 180 days | IRC:SP:83-2008 |
|  | Skid Number | Skid Resistance no. at different speed of vehicles |  |  | Bi-Annually | SCRIM (Sideway-force Coefficient Routine Investigation Machine or equivalent | IRC:SP:83-2008 | 180 days | IRC:SP:83- 2008 |
|  |  | Minimum SN | Traffic Speed (Km/h) |  |  |  |  |  |  |
|  |  | 36 | 50 |  |  |  |  |  |  |
|  |  | 33 | 65 |  |  |  |  |  |  |
|  |  | 32 | 80 |  |  |  |  |  |  |
|  |  | 31 | 90 |  |  |  |  |  |  |
|  |  | 31 | 110 |  |  |  |  |  |  |

| Asset Type | Performance Parameter | Level of Service |  | Frequency of Inspection | Tools/ Equipment | Standards and References for Inspection and Data Analysis | Time limit for Rectification/ Repair | Maintenance Specifications |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Desirable | Acceptable |  |  |  |  |  |
| Embankment/ Slope | Edge drop at shoulders | Nil | 40mm | Daily | Length Measurement Unit like Scale, Tape, Odometer etc. | IRC | 7-15 days | MORT&H Specification 408.4 |
|  | Slope of camber/cross fall | Nil | <2% variation In prescribed slope of Camber /cross fall | Daily |  |  | 7-15 days | MORT&H Specification 408.4 |
|  | Embankment Slopes | Nil | <15 % variation in prescribe side slope | Daily |  |  | 7-15 days | MORT&H Specification 408.4 |
|  | Embankment Protection | Nil | Nil | Daily | NA |  | 7-15 days | MORT&H Specification 408.4 |
|  | Rain Cuts/ Gullies in slope | Nil | Nil | Daily Specially During Rainy Season | NA |  | 7-15 days | MORT&H Specification 408.4 |

In addition to the above performance criterion, the contractor shall strictly maintain the rigid pavements as per requirements in the following table

Table -2: Maintenance Criteria for Rigid Pavements:

| S.No. | Type of Distress |  |  | Measured Parameter | Degree of Severity |  | Assessment Rating |  | Repair Action |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |  |  |
| CRACKING |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 |  | Single DiscreteCracksNotintersecting with any joint | w = width of crack L = length of crack d = depth of crack D = depth of slab |  | 0 | Nil, not discernible |  | No Action |  |  | Not applicable |
|  |  |  |  |  | 1 | w < 0.2 mm. hair cracks |  |  |  |  |  |
|  |  |  |  |  | 2 | w = 0.2 - 0.5 mm, discernible fromslow-moving car |  | Seal without delay |  |  | Seal, and stitch if L >lm. Within 7days |
|  |  |  |  |  | 3 | w = 0.5 - 1.5 mm, discernible fromfast-moving car |  |  |  |  |  |
|  |  |  |  |  | 4 | w = 1.5 - 3.0 mm |  | Seal, and stitch if L > l m. Within 7 days |  |  | Staple or Dowel BarRetrofit, FDR for affected portion. Within 15days |
|  |  |  |  |  | 5 | w > 3 mm. |  |  |  |  |  |
| 2 |  | Single Transverse (or Diagonal) Crackintersecting with oneor more joints | w = width of crack L = length of crack d = depth of crack D = depth of slab |  | 0 | Nil, not discernible |  | No Action |  |  |  |
|  |  |  |  |  | 1 | w < 0.2 mm, hair cracks |  | Route and seal with epoxy. Within 7 days |  |  | Staple or Dowel Bar Retrofit. Within 15days |
|  |  |  |  |  | 2 | w = 0.2 - 0.5 mm, discernible from slow vehicle |  |  |  |  |  |
|  |  |  |  |  | 3 | w = 0.5 - 3.0 mm, discernible fromfast vehicle |  | Route, seal and stitch, if L > 1 m. Within 7 days |  |  |  |
|  |  |  |  |  | 4 | w = 3.0 - 6.0 mm |  | Dowel Bar Retrofit. Within 15 days Not Applicable, as it may be full depth |  |  | Full Depth Repair Dismantle and Reconstruct affected. Portion with norms and specifications - See Para 5.5 & 9.2Within 15days |
|  |  |  |  |  | 5 | w > 6 mm, usually associated with spelling, and/or slab rocking under traffic |  |  |  |  |  |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
| 3 | Single Longitudinal Crack intersecting with one or more joints | w = width of crack L = length of crack d = depth of crack D = depth of slab | 0 | Nil, not discernible | No Action |  |
|  |  |  | 1 | w < 0.5 mm, discernable from slow moving vehicle | Seal with epoxy, if L>1m. Within 7 days | Staple or dowel bar retrofit. Within 15days |
|  |  |  | 2 | w = 0.5 - 3.0 mm, discernible from fast vehicle | Route seal and stitch, if L >l m. Within 15 days | - Partial Depth Repair with stapling. Within 15 days |
|  |  |  | 3 | w = 3.0 - 6.0 mm | Staple, if L > 1 m. Within 15 days |  |
|  |  |  | 4 | w = 6.0 - 12.0 mm, usually associated with spalling | Not Applicable, as it may be full depth |  |
|  |  |  | 5 | w> 12 mm, usually associated with spalling, and/or slab rocking undertraffic |  | Full Depth Repair Dismantle and reconstruct affected portion as per norms and specifications - See Para 5.6.4 Within 15 days |
| 4 | Multiple Cracks intersecting with one or more joints | w = width of crack | 0 | Nil, not discernible | No Action |  |
|  |  |  | 1 | w < 0.2 mm, hair cracks | Seal, and stitch if L > l m. Within 15 days |  |
|  |  |  | 2 | w = 0.2 - 0.5 mm. discernible from slow vehicle |  |  |
|  |  |  | 3 | w = 0.5 - 3.0 mm, discernible from fast vehicle | Full depth repair within 15 days | Dismantle, Reinstate Sub base, Reconstruct whole slab as per specifications within 30 days |
|  |  |  | 4 | w = 3.0 - 6.0 mm panel broken into 2 or 3 pieces |  |  |
|  |  |  | 5 | w > 6 mm and/or panel broken |  |  |

| S.No. | Type of Distress | Measured Parameter |  | Degree of Severity |  | Assessment Rating | Repair Action |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | For the case d < D/2 |  |  | For the case d > D/2 |
| 5 | Corner Break | w = width of crack L = length of crack |  | 0 |  | Nil, not discernible | No Action |  |  |  |
|  |  |  |  | 1 |  | w < 0.5 mm; only 1 corner broken | Seal with low viscosityepoxy to secure broken parts Within 7 days |  |  | Seal with epoxy seal with epoxy Within 7days |
|  |  |  |  | 2 |  | w < 1.5 mm; L < 0.6 m, only one corner broken |  |  |  |  |
|  |  |  |  | 3 |  | w < 1.5 mm; L < 0.6 m, two corners broken | Partial Depth (Refer Figure 8.3 of IRC:SP: 83-2008) Within 15 days |  |  | Full depth repair |
|  |  |  |  | 4 |  | w > 1.5 mm; L > 0.6 m or three corners broken |  |  |  |  |
|  |  |  |  | 5 |  | three or four corners broken |  |  |  | Reinstate sub-base, and reconstruct the slab as per norms and specifications within 30days |
| 6 |  | Punch out (Applicable to Continuous Reinforced Concrete Pavement (CRCP) only) | w = width of crack L = length (m/m2) | 0 |  | Nil, not discernible |  |  | Not Applicable, as it may be full depth | No Action |  |  |
|  |  |  |  | 1 |  | w < 0.5 mm; L < 3 m/m2 |  |  |  | Seal with low viscosity epoxy to secure broken parts. Within 15days |  |  |
|  |  |  |  | 2 |  | either w > 0.5 mm or L < 3m/m2 |  |  |  |  |  |  |
|  |  |  |  | 3 |  | w > 1.5 mm and L < 3 m/m2 |  |  |  |  |  |  |
|  |  |  |  | 4 |  | w > 3 mm, L < 3 m/m2 and deformation |  |  |  | Full depth repair - Cut out and replace damaged area taking care not to damage rein forcement. Within 30days |  |  |
|  |  |  |  | 5 |  | w > 3 mm, L > 3 m/m2 and deformation |  |  |  |  |  |  |

| S.No. |  | Type of Distress |  | Measured Parameter |  | Degree of Severity |  | Assessment Rating | Repair Action |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | For the case d < D/2 |  |  | For the case d > D/2 |
| Surface Defects |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | Short Term |  |  | Long Term |
| 7 | Raveling or Honeycomb type surface |  | r = area damaged surface/total surface of slab (%) h = maximum depth of damage |  | 0 |  | Nil, not discernible |  |  | No Action | Not Applicable |  |  |
|  |  |  |  |  | 1 |  | r < 2 % |  |  | Local repair of areas Damaged and liable to be Damaged.Within 15 days |  |  |  |
|  |  |  |  |  | 2 |  | r = 2 - 10 % |  |  |  |  |  |  |
|  |  |  |  |  | 3 |  | r = 10-25% |  |  | Bonded Inlay, 2 or 3 slabs If affecting.Within 30 days |  |  |  |
|  |  |  |  |  | 4 |  | r = 25 - 50 % |  |  |  |  |  |  |
|  |  |  |  |  | 5 |  | r > 50% and h > 25 mm |  |  | Reconstruct slabs, 4 or more slabs if affecting.Within 30 days |  |  |  |
| 8 |  | Scaling |  | r = damaged surface/total surface of slab (%) h = maximum depth of damage |  | 0 |  | Nil, not discernible | No action. |  |  | Not Applicable |
|  |  |  |  |  |  | 1 |  | r < 2 % | Local repair of areas damaged and liable to be damaged.Within 7days |  |  |  |
|  |  |  |  |  |  | 2 |  | r = 2 - 10 % |  |  |  |  |
|  |  |  |  |  |  | 3 |  | r = 10 - 20% | Bonded Inlay within 15days |  |  |  |
|  |  |  |  |  |  | 4 |  | r = 20 - 30 % |  |  |  |  |
|  |  |  |  |  |  | 5 |  | r > 30 % and h > 25 mm | Reconstruct slab within30 days |  |  |  |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
| 9 | Polished Surface/Glazing | t = texture depth, sand patch test | 0 | Nil | No action. | Not Applicable |
|  |  |  | 1 | t > 1 mm |  |  |
|  |  |  | 2 3 | t = 1 - 0.6 mm 3m/m2 t = 0.6 - 0.3 mm | Monitor rate of deterioration |  |
|  |  |  | 4 | t = 0.3 - 0.1 mm |  |  |
|  |  |  | 5 | t < 0.1 mm | Diamond Grinding if affecting 50% or more slabs in a continuous stretch of minimum5 km. Within 30 days |  |
| 10 | Popout (Small Hole), Pothole Refer Para 8.4 | n = number/m2 d = diameter h = maximum depth | 0 | d < 50 mm; h < 25 mm; n < 1 per 5 m2 | No action. | Not Applicable |
|  |  |  | 1 | d = 50 - 100 mm; h < 50 mm; n < 1 per 5 m2 | Partial depth repair 65mm deep.Within 15 days |  |
|  |  |  | 2 | d = 50 - 100 mm; h > 50 mm; n < 1 per 5 m2 |  |  |
|  |  |  | 3 | d = 100 - 300 mm; h < 100 mm n < 1 per 5 m2 | Partial depth repair 110mm i.e.10 mm more than thedepth of the hole.Within 30 days |  |
|  |  |  | 4 | d = 100 - 300 mm; h > 100 mm; n < 1 per 5 m2 |  |  |
|  |  |  | 5 | d > 300 mm; h > 100 mm: n > 1 per 5 m2 | Full depth repair. Within 30 days |  |

| S.No. |  | Type of Distress |  | Measured Parameter |  | Degree of Severity |  | Assessment Rating |  | Repair Action |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |  |  |
| Joint Defects |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  | Short Term | Long Term |  |  |
| 11 | Joint Seal Defects |  | loss or damage L = Length as % total joint length |  | 0 |  | Difficult to discern |  | No action. |  |  | Not Applicable |
|  |  |  |  |  | 1 |  | Discernible, L< 25% but of little immediate consequence with regard to ingress of water or trapping incompressible material. |  | Clean joint, inspect later. |  |  |  |
|  |  |  |  |  | 2 |  | Notable. L > 25% insufficient protection against ingress of water and trapping incompressible material. |  | Clean and reapply sealant in selected locations.Within 7 days |  |  |  |
|  |  |  |  |  | 3 |  | Severe; w > 3 mm negligible protection against ingress of water and trapping incompressible material. |  | Clean, widen and reseal the joint.Within 7 days |  |  |  |
| 12 |  | Spalling of Joints |  | w = width on either side of the joint L = length of spalled portion (as % joint length) |  | 0 | Nil, not discernible |  |  | No action. | Not Applicable |  |  |
|  |  |  |  |  |  | 1 | w < 10 mm |  |  | Apply low viscosity epoxy resin/mortar in cracked portion.Within 7 days |  |  |  |
|  |  |  |  |  |  | 2 | w = 10 - 20 mm, L < 25% |  |  |  |  |  |  |
|  |  |  |  |  |  | 3 | w = 20 - 40 mm, L > 25% |  |  | Partial Depth Repair Within 15 days |  |  |  |
|  |  |  |  |  |  | 4 | w = 40 - 80 mm, L > 25% |  |  | 30 - 50 mm deep, h = w + 20% of w, within 30 days |  |  |  |
|  |  |  |  |  |  | 5 | w > 80 mm, and L > 25% |  |  | 50-100 mm deep repair. H=w+20%of w.Within 30 days |  |  |  |
| S.No. |  | Type of Distress |  | Measured Parameter |  | Degree of Severity | Assessment Rating |  |  | Repair Action |  |  |  |
|  |  |  |  |  |  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |  |  |
| 13 |  | Faulting (or Stepping) in Cracks or Joints |  | f= difference of level |  | 0 | not discernible, < 1 mm |  |  | No action. | No action. |  |  |
|  |  |  |  |  |  | 1 | f < 3 mm |  |  |  |  |  |  |
|  |  |  |  |  |  | 2 | f = 3 - 6 mm |  |  | Determine cause and bserve, take action for diamond grinding | Replace the slab as appropriate.Within 30days |  |  |
|  |  |  |  |  |  | 3 | f = 6 - 12 mm |  |  | Diamond Grinding |  |  |  |
|  |  |  |  |  |  | 4 | f= 12 - 18 mm |  |  | Raise sunken slab. | Replace the slab as appropriate.Within 30days |  |  |
|  |  |  |  |  |  | 5 | f> 18 mm |  |  | Strengthen sub grade and sub-base by grouting and raising sunken slab |  |  |  |
| 14 |  | Blowup or Buckling |  | h = vertical displacement from normal profile |  |  |  |  |  | Short Term | Long Term |  |  |
|  |  |  |  |  |  | 0 | Nil, not discernible |  |  | No Action |  |  |  |
|  |  |  |  |  |  | 1 | h < 6 mm |  |  |  |  |  |  |
|  |  |  |  |  |  | 2 | h = 6 - 12 mm |  |  | Install Signs to Warn Traffic within 7 days |  |  |  |
|  |  |  |  |  |  | 3 | h = 12 - 25 mm |  |  |  |  |  |  |
|  |  |  |  |  |  | 4 | h > 25 mm |  |  | Full Depth Repair. Within 30 days |  |  |  |
|  |  |  |  |  |  | 5 | shattered slabs, i/e 4 or more pieces |  |  | Replace broken slabs. Within 30 days |  |  |  |

| S.No. | Type of Distress | Measured Parameter |  | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
| 15 | Depression | h = negative vertical displacement from normal profile L =length |  | 0 | Not discernible, h < 5 mm | No Action | Not Applicable |
|  |  |  |  | 1 | h = 5 - 15 mm |  |  |
|  |  |  |  | 2 | h = 15-30 mm, Nos<20% joints | Install Signs to Warn Traffic within 7 days |  |
|  |  |  |  | 3 | h = 30 - 50 mm |  |  |
|  |  |  |  | 4 | h > 50 mm or > 20%joints | Strengthen subgrade.Reinstate pavement at normal level if L < 20 m. Within 30 days |  |
|  |  |  |  | 5 | h > 100 mm |  |  |
| 16 | Heave | h = positive vertical displacement from normal profile. L = length |  |  |  | Short Term | Long Term |
|  |  |  |  | 0 | Not discernible. h < 5 mm | No action. | scrabble |
|  |  |  |  | 1 | h = 5 - 15 mm | Follow up. |  |
|  |  |  |  | 2 | h = 15 - 30 mm, Nos<20% joints | Install Signs to Warn Traffic within 7 days |  |
|  |  |  |  | 3 | h = 30 - 50 mm | Stabilise sub grade. Reinstate pavement at normal level if length< 20 m. Within 30 days |  |
|  |  |  |  | 4 | h > 50 mm or > 20% joints |  |  |
|  |  |  |  | 5 | h > 100 mm |  |  |
| 17 | Bump | h = vertical displacement from normal profile |  | 0 | h < 4 mm | No Action | Construction Limit for New Construction |
|  |  |  |  | 1 | h = 4 - 7 mm | Grind, in case of new construction within 7 days |  |
|  |  |  |  | 3 | h = 7 - 15 mm | Grind, in case of ongoing Maintenance within 15 days | Replace in case of new construction. Within 30days |
|  |  |  |  | 5 | h > 15 mm | Full Depth Repair. Within 30 days | Full Depth Repair. Within 30days |
| S.No. | Type of Distress | Measured Parameter |  | Degree of Severity | Assessment Rating | Repair Action |  |
|  |  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
| 18 | Lane toShoulderDrop off | f = difference of level |  |  |  | Short Term | Long Term |
|  |  |  |  | 0 | Nil, not discernible < 3mm | No action. |  |
|  |  |  |  | 1 | f = 3 - 10 mm | Spot repair of shoulderwithin 7 days |  |
|  |  |  |  | 2 | f = 10 - 25 mm |  |  |
|  |  |  |  | 3 | f = 25 - 50 mm | Fill up shoulder within 7 days | For any 100 m stretch Reconstruct shoulder, if affecting 25% or more of stretch.Within 30days |
|  |  |  |  | 4 | f = 50 - 75 mm |  |  |
|  |  |  |  | 5 | f > 75 mm |  |  |
| Drainage |  |  |  |  |  |  |  |
| 19 | Pumping |  | quantity of fines and water expelled through open joints and cracks Nos/100 m stretch | 0 | not discernible | No action. | Not Applicable |
|  |  |  |  | 1 to 2 | slight/ occasional Nos< 10% | Repair cracks and joints Without delay. | Inspect and repair sub-drainage at distressed sections and upstream. |
|  |  |  |  | 3 to 4 | appreciable/ Frequent 10 - 25% | Lift or jack slab within 30 days. |  |
|  |  |  |  | 5 | abundant, crack development > 25% | Repair distressed pavement sections. Strengthen sub grade and sub base. Replace slab.Within 30 days |  |
| 20 | Ponding |  | Ponding on slabs due to blockage of drains | 0-2 | No discernible problem | No action. |  |
|  |  |  |  | 3 to 4 | Blockages observed in drains, but water flowing | Clean drains etc within 7 days, Follow up | Action required to stop water damaging foundation within 30 days. |
|  |  |  |  | 5 | Ponding, accumulation of water observed | -do |  |

Table -3: Maintenance Criteria for Safety Related Items and Other Furniture Items:

| Asset Type |  |  | Performance Parameter | Level of Service (LOS) |  | Frequency of Measurement |  | Testing Method |  | Recommended Remedial measures |  | Time limit for Rectification |  | Specifications and Standards |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Highway | Availability of Safe Sight Distance |  |  | As per IRC SP : 84-2014, a minimum of safe stopping sight distance shall be available throughout. Design Speed, kmph; Desirable Minimum Sight Distance (m); Safe Stopping Sight Distance (m). 100; 360; 180. 80; 260; 130. | Monthly |  | Manual Measurements with Odometer along with video/ image backup |  | Removal of obstruction within 24 hours, in case of sight line affected by temporary objects such as trees, temporary encroachments. In case of permanent structure or design deficiency: Removal of obstruction/improvement of deficiency at the earliest Speed Restriction boards and suitable traffic calming measures such as transverse bar marking, blinkers, etc. shall be applied during the period of rectification. |  | IRC:SP 84-2014 |  |  |
| Pavement Marking |  |  | Wear | <70% of marking remaining |  | Bi-Annually |  | Visual Assessment asper Annexure-F of IRC:35-2015 |  | Re – painting |  | Cat-1 Defect – within 24 Hours Cat-2 Defect - within 2 months |  | IRC:35-2015 |
|  |  |  | Day time Visibility | During expected life Service Time Cement Road - 130mcd/m2/lux Bituminous Road - 100mcd/m2/ lux |  | Monthly |  | As per Annexure-D of IRC:35-2015 |  | Re – painting |  | Cat-1 Defect – within 24 hours Cat-2 Defect– within 2 months |  | IRC:35-2015 |

| Asset Type | Performance Parameter | Level of Service (LOS) | Frequency of Measurement | Testing Method | Recommended Remedial measures | Time limit for Rectification | Specifications and Standards |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Night Time Visibility | Initial and Minimum Performance for Dry Retro reflectivity during night time: Design Speed; (RL)Retro Reflectivity (mcd/m2/lux). Initial (7 days); Minimum Threshold level(TL) & warranty Period required up to 2 years. Up to 65; 200; 80. 65 – 100; 250; 120. Above 100; 350; 150. Initial and Minimum Performance for Night Visibility under wet condition (Retro reflectivity): Initial 7 days Retro reflectivity: 100 mcd/m2/lux Minimum Threshold Level: 50 mcd/m2/lux | Bi-Annually | As perAnnexure-E of IRC:35-2015 | Re – painting | Cat-1 Defect – within 24 hours Cat-2 Defect – within 2 months | IRC:35-2015 |
|  | Skid Resistance | Initial and Minimum performance for Skid Resistance: Initial (7days): 55BPN Min. Threshold: 44BPN *Note: shall be considered under urban/city traffic condition encompassing the locations likepedestrian crossings, bus bay, bus stop, cycle track intersection delineation, transverse bar markings etc | Bi-Annually | As per Annexure-G of IRC:35-2015 |  | Within 24 hours | IRC:35-2015 |
| Asset Type | Performance Parameter | Level of Service (LOS) | Frequency of Measurement | Testing Method | Recommended Remedial measures | Time limit for Rectification | Specifications and Standards |
| Road Signs | Shape and Position | Shape and Position as per IRC:67- 2012. Signboard should be clearly visible for the design speed of the section. | Daily | Visual with video/image backup | Improvement of shape, in case if shape is damaged. Relocation as per requirement | 48 hours in case of Mandatory Signs, Cautionary and Informatory Signs (Single and Dual post signs) 15 Days in case Of Gantry/ Cantilever Sign boards | IRC:67-2012 |
|  | Retro Reflectivity | As per specifications in IRC:67-2012 | Bi-Annually | Testing of each signboard using Retro Reflectivity Measuring Device. In accordance with ASTM D 4956-09. | Change of Signboard | 48 hours in case of Mandatory Signs, Cautionary and Informatory Signs (Single and Dual post signs) 1 Month in case Of Gantry/ Cantilever Sign boards | IRC:67-2012 |
| Kerb | Kerb Height | As per IRC 86:1983 depending upon type of Kerb | Bi-Annually | Use of distance measuring tape | Raising Kerb Height | Within 1 Month | IRC 86:1983 |
|  | Kerb Painting | Functionality: Functioning of Kerb painting as intended | Daily | Visual withvideo/imagebackup | Kerb Repainting | Within 7-days | IRC 35:2015 |

| Asset Type |  |  | Performance Parameter | Level of Service (LOS) |  | Frequency of Measurement |  | Testing Method |  | Recommended Remedial measures |  | Time limit for Rectification |  | Specifications and Standards |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Other Road Furniture | ReflectivePavementMarkers (Road Studs) |  |  | Numbers and Functionality as per specifications in IRC:SP:84-2014 and IRC:35-2015, unless specified in Schedule-B. |  | Daily |  | Counting |  | New Installation |  | Within 2 months |  | IRC:SP:84-2014, IRC:35- 2015 |  |
|  | Pedestrian Guardrail |  |  | Functionality: Functioning of Guardrail as intended |  | Daily |  | Visual with Video/image backup |  | Rectification |  | Within 15 days |  | IRC:SP:84-2014 |  |
|  | Traffic Safety Barriers |  |  | Functionality: Functioning of Safety Barriers as intended |  | Daily |  | Visual with Video/image backup |  | Rectification |  | Within 7 days |  | IRC:SP:84-2014, IRC:119-2015 |  |
|  | End Treatment of Traffic Safety Barriers |  |  | Functionality: Functioning of End Treatment as intended |  | Daily |  | Visual with Video/image backup |  | Rectification |  | Within 7 days |  | IRC:SP:84-2014, IRC:119-2015 |  |
|  | Attenuators |  |  | Functionality: Functioning of Attenuators as intended |  | Daily |  | Visual with Video/image backup |  | Rectification |  | Within 7 days |  | IRC:SP-2014, IRC:119-2015 |  |
|  | Guard Posts And Delineators |  |  | Functionality: Functioning of Guard Posts and Delineators as intended |  | Daily |  | Visual with Video /image backup |  | Rectification |  | Within 15 days |  | IRC:79 – 1981 |  |
|  | Overhead Sign Structure |  |  | Overhead sign structure shall be structurally adequate |  | Daily |  | Visual with Video /image backup |  | Rectification |  | Within 15 days |  | IRC:67-2012 |  |
|  | Traffic Blinkers |  |  | Functionality: Functioning of Traffic Blinkers as intended |  | Daily |  | Visual with Video /image backup |  | Rectification |  | Within 7 days |  | IRC:SP:84- 2014 |  |
| Asset Type |  |  | Performance Parameter | Level of Service (LOS) |  | Frequency of Measurement |  | Testing Method |  | Recommended Remedial measures |  | Time limit for Rectification |  | Specifications and Standards |  |
| Highway Lighting System | Highway Lights |  |  | Illumination: Minimum 40 Lux illumination on the road surface |  | Daily |  | The llumination level shall be measure with lux meter |  | ImprovementinLightingSystem |  | 24 hours |  | IRC:SP:84-2014 |  |
|  |  |  |  | No major failure in the lightingSystem |  | Daily |  | - |  | Rectification of failure |  | 24 hours |  | IRC:SP:84-2014 |  |
|  |  |  |  | No minor failure in the lightingSystem |  | Monthly |  | - |  | Rectification of failure |  | 8 hours |  | IRC:SP:84-2014 |  |
|  | Toll Plaza Canopy Lights |  |  | Minimum 40 Lux illumination on the road surface |  | Daily |  | Theillumination level shall be measured with lux meter |  | Improvement in Lighting System |  | 24 hours |  | IRC:SP:84-2014 |  |
|  |  |  |  | No major/minor failure in the lighting system |  | Daily |  | - |  | Rectification of failure |  | 8 hours |  | IRC:SP:84-2014 |  |

| Asset Type |  |  |  | Performance Parameter |  | Level of Service (LOS) |  |  |  | Frequency of Measurement |  |  | Testing Method |  | Recommended Remedial measures |  |  |  | Time limit for Rectification |  | Specifications and Standards |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tree andPlantationincludingmedianplantation |  |  |  | Obstructionin a minimum head-room of5.5 m above carriagewayor obstruction in visibility ofroad signs |  | No obstruction due to trees |  |  |  | Monthly |  |  | Visual with video/image backup |  | Removal of trees |  |  | Immediate |  |  | IRC:SP:84- 2014 |  |  |
|  |  |  |  | Deterioration in health of trees and bushes |  | Health of plantation shall be as per requirement of specifications & instructions issued by Authority from time to time |  |  |  | Daily |  |  | Visual with video/image backup |  | Timely watering and treatment. or Replacementof Trees andBushes. |  |  |  | Within 90 days |  | IRC:SP:84- 2014 |  |  |
|  |  |  |  | Vegetation affecting sight line and road structures |  | Sight line shall be free from obstruction by vegetation |  |  |  | Daily |  |  | Visual with video/image backup |  | Removal of Trees |  |  |  | Immediate |  | IRC:SP 84- 2014 |  |  |
| Rest Areas |  |  |  | Cleaning of Toilets |  | - |  |  |  | Daily |  |  | - |  | - |  |  |  | Every 4 hours |  |  |  |  |
|  |  |  |  | Defects in electrical, water and sanitary installations |  | - |  |  |  | Daily |  |  | - |  | Rectification |  |  |  | 24 hours |  |  |  |  |
| Other Project Facilities and Approachroads |  |  |  | Damage or deterioration in Approach Roads, pedestrian facilities, truck lay-bys, bus-bays, busshelters, cattle crossings, Traffic Aid Posts, Medical Aid Posts and other works |  |  |  |  |  | Daily |  |  | - |  | Rectification |  |  |  | 15 days |  | IRC:SP 84- 2014 |  |  |
| Asset Type |  | Performance Parameter |  |  | Level of Service (LOS) |  |  | Frequency of Measurement |  |  | Testing Method |  |  | Recommended Remedial measures |  |  | Time limit for Rectification |  |  |  |  | Specifications and Standards |  |  |
| Pipe/ box/ slab culverts |  | Free waterway /unobstructed flow section |  |  |  | 85% of culvert normal flow area to available. |  | 2 times in a year (before and after rainy season) |  |  | Inspection by Bridge Engineer as per IRC SP: 35-1990 and recording of depth of silting and area of vegetation. |  |  |  | Cleaning silt up soils and debris in culvert barrel after rainy season, removal of bushes and vegetation, U/s of barrel, under barrel and D/s of barrel before rainy season. |  |  |  | 15 days before onset of monsoon and within 30 days after end of rainy season. |  |  | IRC 5-2015, IRC SP:40- 1993 and IRC SP:13- 2004 |  |  |
|  |  | Leak-proof expansion joints if any |  |  |  | No leakage through expansion joints |  | Bi-Annually |  |  | Physical inspection of expansion joints as per IRC SP: 35- 1990 if any, for leakage strains on walls at joints. |  |  |  | Fixing with sealant Suitably |  |  |  | 30 days or before onset of rains whichever Comes earlier |  |  | IRC SP:40- 1993 and IRC SP:69-2011 |  |  |
|  |  | Structurally sound |  |  |  | Spalling of concrete not more than 0.25 sqm |  | Bi-Annually |  |  | Detailed inspection of all components of culvert as per IRC SP:35-1990 and recording the defects |  |  |  | Repairs to spalling, cracking, delamination, rusting shall be followed as per IRC:SP: 40-1993. |  |  |  | 15 days |  |  | IRC SP 40- 1993 and MORTH Specifications clause 2800 |  |  |
|  |  | Delamination of concrete not more than 0.25 sq.m. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Cracks wider than 0.3 mm not more than 1m aggregate length |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Protection works in good condition |  |  |  | Damaged of rough stone apron or bank revetment not more than 3 sqm, damage to solid apron (concrete apron) not more than 1 sqm |  | 2 times in a year (before and after Rainy season) |  |  | Condition survey as per IRC SP:35-1990 |  |  |  | Repairs to damaged aprons and pitching |  |  |  | 30 days after defect observation or 2 weeks before onset of rainy Season whichever is earlier. |  |  | IRC: SP 40- 1993 and IRC:SP:13- 2004. |  |  |

| Asset Type | Performance Parameter | Level of Service (LOS) | Frequency of Measurement | Testing Method | Recommended Remedial measures | Time limit for Rectification | Specifications and Standards |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Bridges including ROBs Flyover etc. as applicable | Riding quality or User comfort | No pothole in wearing coat on bridge deck | Daily | Visual inspection as per IRC SP:35-1990 | Repairs to BC or wearing coat | 15 days | MORT&H Specification2811 |  |  |
| Bridge -Super Structure | Bumps | No bump at expansion joint | Daily | Visual inspection as per IRC SP:35- 1990 | Repairs to BC on either side of expansion joints,profile correction course on approach slab in case of settlement to approach embankment | 15 days | MORT&H Specification 3004.2 & 2811. |  |  |
|  | User safety (condition of crash barrier and guard rail) | No damaged or missing stretch of crash barrier or pedestrian hand railing | Daily | Visual inspection and detailed condition survey as per IRC SP:35-1990. | Repairs and replacement of safety barriers as the case may be | 3days | IRC: 5-1998, IRC SP: 84-2014 and IRC SP: 40-1993. |  |  |
|  | Rusted reinforcement | Not more than 0.25 sq.m | Bi- Annually | Detailed condition survey as per IRC SP: 35-1990 using Mobile Bridge Inspection Unit | All the corroded reinforcement shall need to be thoroughly cleaned from rusting and applied with anti-corrosive coating before carrying out the repairs to affected concrete portion with epoxy mortar / concrete. | 15 days | IRC SP: 40-1993 andMORTH Specification 1600. |  |  |
|  | Spalling of concrete | Not more than 0.50 sq.m |  |  |  |  |  |  |  |
|  | Delamination | Not more than 0.50 sq.m |  |  |  |  |  |  |  |
|  | Cracks wider than 0.30 mm | Not more than 1m total length | Bi-Annually | Detailed condition survey as per IRC SP: 35-1990 using Mobile Bridge Inspection Unit | Grouting with epoxy mortar, investigatingcauses for cracksdevelopment and carry out necessaryrehabilitation. | 48 Hours | IRC:SP:40-1993 andMORTH Specification2800. |  |  |
| Asset Type | Performance Parameter | Level of Service (LOS) | Frequency of Measurement | Testing Method | Recommended Remedial measures | Time limit for Rectification | Specifications and Standards |  |  |
|  | Rainwater seepage hrough deck slab | Leakage – nil | Quarterly | Detailed condition survey as per IRC SP:35-1990 using Mobile Bridge Inspection Unit | Grouting of deck slab at leakage areas, waterproofing, repairs to drainage spouts | 1 months | MORTH specifications 2600 & 2700. |  |  |
|  | Deflection due to Permanent loads and live loads | Within design limits. | Once in every 10 years forspans more than 40 m | Load test method | Carryout majorrehabilitation works on bridge to retain original design loads capacity | 6 months | IRC SP: 51- 1999. |  |  |
|  | Vibrations in bridge deck due to moving trucks | Frequency of vibrations shall not be more than 5 Hz | Once in every 5 years for spans more than 30m and every 10 years for spans between 15to30m | Laser displacement sensors or laser vibro-meters | Strengthening of super Structure | 4 months | AASHTO LRFD specifications |  |  |
|  | Leakage in Expansion joints | No damage to elastomeric sealant compound in strip seal expansion joint, no leakage of rain water through expansion joint in case of buried and asphalt plug and copper strip joint. | Bi-Annually | Detailed condition survey as per IRC SP:35-1990 using Mobile Bridge Inspection Unit | Replace of seal in expansion joint | 15 days | MORTH specifications 2600 and IRC SP: 40-1993. |  |  |
|  | Debris and dust in strip seal expansion joint | No dust or debris in expansion joint gap. | Monthly | Detailed condition survey as per IRC SP: 35 -1990 using Mobile Bridge Inspection Unit | Cleaning of expansion joint gaps thoroughly | 3 days | MORTH specifications 2600 and IRC SP: 40- 1993. |  |  |
| Asset Type | Performance Parameter | Level of Service (LOS) | Frequency of Measurement | Testing Method | Recommended Remedial measures | Time limit for Rectification |  | Specifications and Standards |
|  | Drainage spouts | No down take pipe missing/broken below soffit of the deck slab. No silt, debris, clogging of drainage spout collection chamber. | Monthly | Detailed condition survey as per IRC SP:35-1990 using Mobile Bridge Inspection Unit | Cleaning of drainage spouts thoroughly. Replacement of missing /broken down take pipes with a minimum pipe extension of 500 mm below soffit of slab. Providing sealant around the drainage spout if any leakages observed. | 3 days |  | MORTH specification 2700. |
| Bridge substructure | Cracks/spalling of concrete/ rusted steel | No cracks, spalling of concrete and rusted steel | Bi-Annually | Detailed condition survey as per IRC SP: 35-1990 using Mobile Bridge Inspection Unit | All the corroded reinforcement shall need to be thoroughly cleaned from rusting and applied with anti-corrosive coating before carrying out repairs to sub structurebygrouting/gunitingandmicroconcretingdepending on type ofdefect noticed | 30 days |  | IRC SP: 40- 1993 and MORTH specification 2800. |
|  | Bearings | Delamination of Bearing reinforcement not more than 5%, cracking or tearing of rubber not more than 2 locations per side, no rupture of reinforcementor rubber | Bi-Annually | Detailed condition survey as per IRC SP: 35-1990 using Mobile Bridge Inspection Unit | In case of failure of even one bearing on any pier/ abutment, all the bearings on that pier/ abutment shall be replaced, in order to get uniform load transfer on to bearings. | 3 months |  | MORTH specificatio n 2810 and IRC SP: 40- 199. |

| Asset Type | Performance Parameter | Level of Service (LOS) | Frequency of Measurement | Testing Method | Recommended Remedial measures | Time limit for Rectification | Specifications and Standards |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Bridge Foundations | Scouring around foundations | Scouring shall not be lower than maximum scour level for the bridge | Bi-Annually | Condition survey and visual inspection as per IRC SP:35-1990 using Mobile Bridge Inspection Unit. In case of doubt, use Underwater camera for inspection of deep wells in major Rivers. | Suitable protectionworks around pier/ abutment | 1 month | IRC SP:40-1993, IRC:83-2014,MORTH specification 2500 |
|  | Protection works in good condition | Damaged of rough stone apron or bank revetment not more than 3 Sq.m, damage to solid apron (concrete apron) not more than 1 sq.m | 2 times in a year (before and after rainy season) | Condition survey as per IRC SP:35- 1990 | Repairs to damaged aprons and pitching. | 30 days after Defect observation or 2 weeks before onset of rainy season whichever is earlier. | IRC: SP 40- 1993 and IRC:SP:13- 2004. |
| Note: Any Structure during the entire contract period which is found that does not complies with all requirements of this Table will be prepared, rehabilitated or even reconstructed under the scope of the contractor. |  |  |  |  |  |  |  |

Table 4: Maintenance Criteria for Structures and Culverts:

Table 5 :	Maintenance Criteria for Hill Roads

In addition to above, for hill roads the following provisions for maintenance is also to done.

| Hill Roads |  |  |
| --- | --- | --- |
| (i) | Damage to Retaining wall/ Breast wall | 7 (Seven) days |
| (ii) | Landslides requiring clearance | 12 (Twelve) hours |
| (iii) | Snow requiring clearance | 24 (Twenty Four) hours |

Note: 	For all tables 1 to 5 above, latest BIS & IRC standards (even those not indicated herewith) along with MoRTH specifications shall be binding for all maintenance activities.

A.	Flexible Pavement

| Nature of Defect or deficiency |  |  |  |  | Time limit for repair/rectification |
| --- | --- | --- | --- | --- | --- |
| (a) Granular earth shoulders, side slopes, drains and culverts |  |  |  |  |  |
| (i) | Variation by more than 1 % in the prescribed slope of camber/cross fall (shall not be less than the camber on the main carriageway) |  |  |  | 7 (seven) days |
| (ii) | Edge drop at shoulders exceeding 40 mm |  |  |  | 7 (seven) days |
| (iii) | Variation by more than 15% in the prescribed side (embankment) slopes |  |  |  | 30 (thirty) days |
| (iv) | Rain cuts/gullies in slope |  |  |  | 7 (seven) days |
| (v) | Damage to or silting of culverts and side drains |  |  |  | 7 (seven) days |
| (vi) | Desilting of drains in urban/semi- urban areas |  |  |  | 24 (twenty four) hours |
| (vii) | Railing, parapets, crash barriers |  |  |  | 7 (seven) days (Restore immediately if causing safety hazard) |
| (b) Road side furniture including road sign and pavement marking |  |  |  |  |  |
| (i) |  | Damage to shape or position, poor visibility or loss of retro- reflectivity |  |  | 48 (forty eight) hours |
| (ii) |  | Painting of km stone, railing, parapets, crash barriers |  |  | As and when required/ Once every year |
| (iii) |  | Damaged/missing signs road requiring replacement |  |  | 7 (seven) days |
| (iv) |  | Damage to road mark ups |  |  | 7 (seven) days |
| (c) Road lighting |  |  |  |  |  |
| (i) |  | Any major failure of the system |  |  | 24 (twenty four) hours |
| (ii) |  | Faults and minor failures |  |  | 8 (eight) hours |
| (d) Trees and plantation |  |  |  |  |  |
| (i) |  |  | Obstruction in a minimum head- room of 5 m above carriageway or obstruction in visibility of road signs |  | 24 (twenty four)hours |
| (ii) |  |  | Removal of fallen trees from carriageway |  | 4 (four) hours |
| (iii) |  |  | Deterioration in health of trees and bushes |  | Timely watering and treatment |
| (iv) |  |  | Trees and bushes requiring replacement |  | 30 (thirty) days |
| (v) |  |  | Removal of vegetation affecting sight line and road structures |  | 15 (fifteen) days |
| Nature of Defect or deficiency |  |  |  |  | Time limit for repair/ rectification |
| (e) Rest area |  |  |  |  |  |
| (i) |  |  | Cleaning of toilets |  | Every 4 (four) hours |
| (ii) |  |  | Defects in electrical, water and sanitary installations |  | 24 (twenty four) hours |
| (f) [Toll Plaza] |  |  |  |  |  |
| (g) Other Project Facilities and Approach roads |  |  |  |  |  |
| (i) |  |  | Damage in approach roads, pedestrian facilities, truck lay- byes, bus-bays, bus-shelters, cattle crossings, [Traffic Aid Posts, Medical Aid Posts] and service roads |  | 15 (fifteen) days |
| (ii) |  |  | Damaged vehicles or debris on the road |  | 4 (four) hours |
| (iii) |  |  | Malfunctioning of the mobile crane |  | 4 (four) hours |
| Bridges |  |  |  |  |  |
| (a) Superstructure |  |  |  |  |  |
| (i) |  |  |  | Any damage, cracks, spalling/ scaling Temporary measures Permanent measures | within 48 (forty eight) hourswithin 15 (fifteen) days or asspecified by the Authority’s Engineer |
| (b) Foundations |  |  |  |  |  |
| (i) |  |  |  | Scouring and/or cavitation | 15 (fifteen) days |
| (c) Piers, abutments, return walls and wing walls |  |  |  |  |  |
| (i) |  |  |  | Cracks and damages including settlement and tilting, spalling, scaling | 30 (thirty) days |
| (d) Bearings (metallic) of bridges |  |  |  |  |  |
| (i) |  |  |  | Deformation, damages, tilting or shifting of bearings | 15 (fifteen) days Greasing of metallic bearings once in a year |
| (e) Joints |  |  |  |  |  |
| (i) |  |  |  | Malfunctioning of joints | 15 (fifteen) days |

| Nature of Defect or deficiency |  | Time limit for repair/ rectification |
| --- | --- | --- |
| (f) Other items |  |  |
| (i) | Deforming of pads in elastomeric bearings | 7 (seven) days |
| (ii) | Gathering of dirt in bearings and joints; or clogging of spouts, weep holes and vent-holes | 3 (three) days |
| (iii) | Damage or deterioration in kerbs, parapets, handrails and crash barriers | 3 (three) days immediately within 24 hours if posing danger to safety |
| (iv) | Rain-cuts or erosion of banks of the side slopes of approaches | 7 (seven) days |
| (v) | Damage to wearing coat | 15 (fifteen) days |

| (vi) | Damage or deterioration in approach slabs, pitching, apron, toes, floor or guide bunds | 30 (thirty) days |
| --- | --- | --- |
| (vii) | Growth of vegetation affecting the structure or obstructing the waterway | 15 (fifteen) days |
| (g) Hill Roads |  |  |
| (i) | Damage to retaining wall/breast wall | 7 (seven) days |
| (ii) | Landslides requiring clearance | 12 (twelve) hours |
|  | Nature of Defect or deficiency | Time limit for repair/rectification |
| (iii) | Snow requiring clearance | 24 (twenty four) hours |

[Note: 	Where necessary, the Authority may modify the time limit for repair/rectification, or add to the nature of Defect or deficiency before issuing the bidding document, with the approval of the competent authority.]

Schedule - F

(See Clause 4.1 (vii)(a))

Applicable Permits

1. 	Applicable Permits

(i) 	The Contractor shall obtain, as required under the Applicable Laws, the following Applicable Permits:

(a)	Permission of the State Government for extraction of boulders from quarry;

(b) 	Permission of Village Panchayats and Pollution Control Board for installation of crushers;

(c) 	Licence for use of explosives;

(d) 	Permission of the State Government for drawing water from river/reservoir;

(e) 	Licence from inspector of factories or other competent Authority for setting up batching plant;

(f) 	Clearance of Pollution Control Board for setting up batching plant;

(g) 	Clearance of Village Panchayats and Pollution Control Board for setting up asphalt plant;

(h) 	Permission of Village Panchayats and State Government for borrow earth; and

(i)	Any other permits or clearances required under Applicable Laws.

(ii) 	Applicable Permits, as required, relating to environmental protection and conservation shall have been procured by the Authority in accordance with the provisions of this Agreement.

Schedule – G

(See Clauses 7.1 and 19.2)

Annex-I

(See Clause 7.1)

Form of Bank Guarantee

[Performance Security/Additional Performance Security]

The Chief Engineer,

PWD, National Highway Zone,

Pension Bada, Raipur (C.G.)

WHEREAS:

________________________________________[name and address of contractor] (hereinafter called the “Contractor") and [name and address of the authority], (hereinafter called the “Authority”) have entered into an agreement (hereinafter called the “Agreement”) for theConstruction of H.L.Bridge at Kosanala in km.306.00 and Construction(Repairing)H.L.Bridge at Kharun River in km.. 283.400 of N.H. 53 ,InChhattishgarh State On Engineering Procurement & Construction (EPC)Basis Contract.

- ., subject to and in accordance with the provisions of the Agreement

- The Agreement requires the Contractor to furnish a Performance Security for due and faithful performance of its obligations, under and in accordance with the Agreement, during the {Construction Period/ Defects Liability Period and Maintenance Period} (as defined in the Agreement) in a sum of Rs….. cr. (Rupees………..….. crore) (the “Guarantee Amount”).

(C) 	We, …………………..through our branch at …………………. (the “Bank”) have agreed to furnish this bank guarantee (hereinafter called the “Guarantee”) by way of Performance Security.

NOW, THEREFORE, the Bank hereby, unconditionally and irrevocably, guarantees and affirms as follows:

1. 	The Bank hereby unconditionally and irrevocably guarantees the due and faithful performance of the Contractor’s obligations during the {Construction Period/Defects Liability Period and Maintenance Period} under and in accordance with the Agreement, and agrees and undertakes to pay to the Authority, upon its mere first written demand, and without any demur, reservation, recourse, contest or protest, and without any reference to the Contractor, such sum or sums up to an aggregate sum of the Guarantee Amount as the Authority shall claim, without the Authority being required to prove or to show grounds or reasons for its demand and/or for the sum specified therein.

2.	A letter from the Authority, under the hand of an officer not below the rank of [General Manager in the National Highways Authority of India], that the Contractor has committed default in the due and faithful performance of all or any of its obligations under and in accordance with the Agreement shall be conclusive, final and binding on the Bank. The Bank further agrees that the Authority shall be the sole judge as to whether the Contractor is in default in due and faithful performance of its obligations during and under the Agreement and its decision that the Contractor is in default shall be final and binding on the Bank, notwithstanding any differences between the Authority and the Contractor, or any dispute between them pending before any court, tribunal, arbitrators or any other authority or body, or by the discharge of the Contractor for any reason whatsoever.

- In order to give effect to this Guarantee, the Authority shall be entitled to act as if the Bank were the principal debtor and any change in the constitution of the Contractor and/or the Bank, whether by their absorption with any other body or corporation or otherwise, shall not in any way or manner affect the liability or obligation of the Bank under this Guarantee.

4. 	It shall not be necessary, and the Bank hereby waives any necessity, for the Authority to proceed against the Contractor before presenting to the Bank its demand under this Guarantee.

5. 	The Authority shall have the liberty, without affecting in any manner the liability of the Bank under this Guarantee, to vary at any time, the terms and conditions of the Agreement or to extend the time or period for the compliance with, fulfillment and/ or performance of all or any of the obligations of the Contractor contained in the Agreement or to postpone for any time, and from time to time, any of the rights and powers exercisable by the Authority against the Contractor, and either to enforce or forbear from enforcing any of the terms and conditions contained in the Agreement and/or the securities available to the Authority, and the Bank shall not be released from its liability and obligation under these presents by any exercise by the Authority of the liberty with reference to the matters aforesaid or by reason of time being given to the Contractor or any other forbearance, indulgence, act or omission on the part of the Authority or of any other matter or thing whatsoever which under any law relating to sureties and guarantors would but for this provision have the effect of releasing the Bank from its liability and obligation under this Guarantee and the Bank hereby waives all of its rights under any such law.

6. 	This Guarantee is in addition to and not in substitution of any other guarantee or security now or which may hereafter be held by the Authority in respect of or relating to the Agreement or for the fulfillment, compliance and/or performance of all or any of the obligations of the Contractor under the Agreement.

7. 	Notwithstanding anything contained hereinbefore, the liability of the Bank under this Guarantee is restricted to the Guarantee Amount and this Guarantee will remain in force for the period specified in paragraph 8 below and unless a demand or claim in writing is made by the Authority on the Bank under this Guarantee all rights of the Authority under this Guarantee shall be forfeited and the Bank shall be relieved from its liabilities hereunder.

8. 	The Guarantee shall cease to be in force and effect on ****$. Unless a demand or claim under this Guarantee is made in writing before expiry of the Guarantee, the Bank shall be discharged from its liabilities hereunder.

9. 	The Bank undertakes not to revoke this Guarantee during its currency, except with the previous express consent of the Authority in writing, and declares and warrants that it has the power to issue this Guarantee and the undersigned has full powers to do so on behalf of the Bank.

10. 	Any notice by way of request, demand or otherwise hereunder may be sent by post addressed to the Bank at its above referred branch, which shall be deemed to have been duly authorized to receive such notice and to effect payment thereof forthwith, and if sent by post it shall be deemed to have been given at the time when it ought to have been delivered in due course of post and in proving such notice, when given by post, it shall be sufficient to prove that the envelope containing the notice was posted and a certificate signed by an officer of the Authority that the envelope was so posted shall be conclusive.

11. 	This Guarantee shall come into force with immediate effect and shall remain in force and effect for up to the date specified in paragraph 8 above or until it is released earlier by the Authority pursuant to the provisions of the Agreement.

Signed and sealed this ………. day of ……….., 20……… at ………..

SIGNED, SEALED AND DELIVERED

For and on behalf of the Bank by:

(Signature)

(Name)

(Designation)

(Code Number)

(Address)

NOTES:

(i) 	The bank guarantee should contain the name, designation and code number of the officer(s) signing the guarantee.

(ii) 	The address, telephone number and other details of the head office of the Bank aswell as of issuing branch should be mentioned on the covering letter of issuing branch.

$ Insert date being 2 (two) years from the date of issuance of this Guarantee (in accordance with Clause 7.2 of the Agreement).

Annex – II

(Schedule - G)

(See Clause 19.2)

Form for Guarantee for Advance Payment

[DG(RD)&SS,

Ministry of Road Transport & Highways Transport Bhawan, New Delhi]

WHEREAS :

(A)	[name and address of contractor] (hereinafter called the “Contractor") has executed an agreement (hereinafter called the “Agreement”) with the [name and address of the authority], (hereinafter called the “Authority”) for Construction Of Rcc Crash Barrier Between  Main Carriageway And Service Road In    Km.281.600 To Km. 307.600,  Of N.H. 53 (Old N.H.06) In Chhattishgarh State Under Road Safty Work

.

., subject to and in accordance with the provisions of the Agreement.

(B)	In accordance with Clause 19.2 of the Agreement, the Authority shall make to the Contractor an interest bearing @Bank Rate + 3% advance payment (herein after called “Advance Payment”) equal to 10% (ten per cent) of the Contract Price; and that the Advance Payment shall be made in two installments subject to the Contractor furnishing an irrevocable and unconditional guarantee by a scheduled bank for an amount equivalent to 110% (one hundred and ten percent) of such installment to remain effective till the complete and full repayment of the installment of the Advance Payment as security for compliance with its obligations in accordance with the Agreement. The amount of {first/second} installment of the Advance Payment is Rs. ------ cr. (Rupees ------ crore) and the amount of this Guarantee is Rs. ------- cr. (Rupees ------ crore) (the “Guarantee Amount”)$.

(C) 	We, …………………..through our branch at …………………. (the “Bank”) have agreed to furnish this bank guarantee (hereinafter called the “Guarantee”) for the Guarantee Amount.

NOW, THEREFORE, the Bank hereby, unconditionally and irrevocably, guarantees and affirms as follows:

1. 	The Bank hereby unconditionally and irrevocably guarantees the due and faithful repayment on time of the aforesaid instalment of the Advance Payment under and in accordance with the Agreement, and agrees and undertakes to pay to the Authority, upon its mere first written demand, and without any demur, reservation, recourse, contest or protest, and without any reference to the Contractor, such sum or sums up to an aggregate sum of the Guarantee Amount as the Authority shall claim, without the Authority being required to prove or to show grounds or reasons for its demand and/or for the sum specified therein.

A letter from the Authority, under the hand of an officer not below the rank of [General Manager in the National Highways Authority of India], that the Contractor has committed default in the due and faithful performance of all or any of its obligations for the repayment of the instalment of the Advance Payment under and in accordance with the Agreement shall be conclusive, final and binding on the Bank. The Bank further agrees that the Authority shall be the sole judge as to whether the Contractor is in default in due and faithful performance of its obligations during and under the Agreement and its decision that the Contractor is in default shall be final and binding on the Bank, notwithstanding any differences between the Authority and the Contractor, or any dispute between them pending before any court, tribunal, arbitrators or any other authority or body, or by the discharge of the Contractor for any reason whatsoever.

2.	In order to give effect to this Guarantee, the Authority shall be entitled to act as if the Bank were the principal debtor and any change in the constitution of the Contractor and/or the Bank, whether by their absorption with any other body or corporation or otherwise, shall not in any way or manner affect the liability or obligation of the Bank under this Guarantee.

3. 	It shall not be necessary, and the Bank hereby waives any necessity, for the Authority to proceed against the Contractor before presenting to the Bank its demand under this Guarantee.

4. 	The Authority shall have the liberty, without affecting in any manner the liability of the Bank under this Guarantee, to vary at any time, the terms and conditions of the Advance Payment or to extend the time or period of its repayment or to postpone for any time, and from time to time, any of the rights and powers exercisable by the Authority against the Contractor, and either to enforce or forbear from enforcing any of the terms and conditions contained in the Agreement and/or the securities available to the Authority, and the Bank shall not be released from its liability and obligation under these presents by any exercise by the Authority of the liberty with reference to the matters aforesaid or by reason of time being given to the Contractor or any other forbearance, indulgence, act or omission on the part of the Authority or of any other matter or thing whatsoever which under any law relating to sureties and guarantors would but for this provision have the effect of releasing the Bank from its liability and obligation under this Guarantee and the Bank hereby waives all of its rights under any such law.

5. 	This Guarantee is in addition to and not in substitution of any other guarantee or security now or which may hereafter be held by the Authority in respect of or relating to the Advance Payment.

6. 	Notwithstanding anything contained hereinbefore, the liability of the Bank under this Guarantee is restricted to the Guarantee Amount and this Guarantee will remain in force for the period specified in paragraph 8 below and unless a demand or claim in writing is made by the Authority on the Bank under this Guarantee all rights of the Authority under this Guarantee shall be forfeited and the Bank shall be relieved from its liabilities hereunder.

7. 	The Guarantee shall cease to be in force and effect on ****.$ Unless a demand or claim under this Guarantee is made in writing on or before the aforesaid date, the Bank shall be discharged from its liabilities hereunder.

8. 	The Bank undertakes not to revoke this Guarantee during its currency, except with the previous express consent of the Authority in writing, and declares and warrants that it has the power to issue this Guarantee and the undersigned has full powers to do so on behalf of the Bank.

9. 	Any notice by way of request, demand or otherwise hereunder may be sent by post addressed to the Bank at its above referred branch, which shall be deemed to have been duly authorized to receive such notice and to effect payment thereof forthwith, and if sent by post it shall be deemed to have been given at the time when it ought to have been delivered in due course of post and in proving such notice, when given by post, it shall be sufficient to prove that the envelope containing the notice was posted and a certificate signed by an officer of the Authority that the envelope was so posted shall be conclusive.

10. 	This Guarantee shall come into force with immediate effect and shall remain in force and effect up to the date specified in paragraph 8 above or until it is released earlier by the Authority pursuant to the provisions of the Agreement.

Signed and sealed this ………. day of ……….., 20……… at ………..

SIGNED, SEALED AND DELIVERED

For and on behalf of the Bank by:

(Signature)

(Name)

(Designation)

(Code Number)

(Address)

NOTES :

(i) 	The bank guarantee should contain the name, designation and code number of the officer(s) signing the guarantee.

(ii) 	The address, telephone number and other details of the head office of the Bank as well as of issuing branch should be mentioned on the covering letter of issuing branch.

$ Insert a date being 90 (ninety) days after the end of one year from the date of payment of the Advance payment to the Contractor (in accordance with Clause 19.2 of the Agreement).

## SCHEDULE – H

## See Clauses10.1 (iv) and 19.3

## Contract Price Weightages

  - The Contract Price for this Agreement is Rs.- 22.50 crore (Including GST)

  - Proportions of the Contract Price for different stages of Construction of the Project Highway shall be as specifiedbelow:

| S. No. | Item | Weightage in percentage to the Contract Price | Stage for Payment | Percentage weightage |
| --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 |
| 1 | Road works In RCC Crash Barrier | 100% | A - Widening and strengthening of existing road |  |
|  |  |  | (1) Earthwork up to top of the subgrade | 0.00% |
|  |  |  | (2) Sub base course (GSB) | 0.00% |
|  |  |  | (3) Non-bituminous base course (WMM) | 0.00% |
|  |  |  | (4) Bituminous base course (DBM) | 0.00% |
|  |  |  | (5) wearing coat (BC) | 0.00% |
|  |  |  | (6) widening and repair of culverts | 0.00% |
|  |  |  | B.1 - Reconstruction realignment/ bypass (Flexible pavement) |  |
|  |  |  | (1) Earthwork up to top of the subgrade | 0.00% |
|  |  |  | (2) Sub base course (GSB) | 0.00% |
|  |  |  | (3) Non-bituminous base course (WMM) | 0.00% |
|  |  |  | (4) Bituminous base course (DBM) | 0.00% |
|  |  |  | (5) wearing coat (BC) | 0.00% |
|  |  |  | B.2-Reconstruction realignment / bypass/ RCC Crash Barrier (Rigid RCC concrete crash barrier) |  |
|  |  |  | (1) Earthwork up to top of the subgrade | 0.18% |
|  |  |  | (2)Plain Cement Concrete (PCC M-20) | 14.35% |
|  |  |  | (3) RCC Crash Barrier M-25 | 78.52% |
|  |  |  | (4) Reconstruction of RCC Crash Barrier M-25 | 4.05 % |
|  |  |  | (5) Painting | 2.90 % |
|  |  |  | C.1 - Reconstruction/ New Service Road (flexible Pavement) |  |
|  |  |  | (1) Earthwork up to top of the subgrade | 0.00% |
|  |  |  | (2) Subbase course (GSB) | 0.00% |
|  |  |  | (3) Non-bituminous base course (WMM) | 0.00% |
|  |  |  | (4) Bituminous base (DBM) | 0.00% |
|  |  |  | (5) wearing coat (BC) | 0.00% |
|  |  |  | C.2 - Reconstruction/ New Service road (Rigid Pavement) |  |
|  |  |  | (1) Earthwork up to top of the subgrade | 0.00% |
|  |  |  | (2) Subbase course (GSB) | 0.00% |
|  |  |  | (3) Dry lean concrete (DLC) | 0.00% |
|  |  |  | (4) Pavement quality concrete (PQC) course | 0.00% |
|  |  |  | D. - Reconstruction/ New culverts on existing road, realignment, bypasses | 0.00% |
| 2 | Minor Bridges/ Underpasses/ Overpasses |  | A.1 - Widening and repairs of Minor Bridges |  |
|  |  |  | Widening of existing bridges | 0.00% |
|  |  |  | rehabilitation of existing bridges | 0.00% |
|  |  |  | A.2 - New of Minor Bridges |  |
|  |  |  | (1) Foundation + Substructure: On completion of the foundation work including foundations for wing and return walls, abutments, piers up to the abutment/pier cap | 0.00% |
|  |  |  | (2) Super-structure: On completion of the super-structure in all respects including wearing coat, bearings, expansion joints, hand rails, crash barriers, road signs & markings, tests on completion etc. complete in all respect. | 0.00% |
|  |  |  | (3) Approaches: On completion of approaches including Retaining walls, stone pitching, protection works complete in all respect and fit for use. | 0.00% |
|  |  |  | (4) Guide Bunds and River Training works: (On completion of Guide Bunds and river training works complete in all respects.) | 0.00% |
|  |  |  | B.1 - Widening and repairs of Underpasses/Overpasses |  |
|  |  |  | Underpasses/ Overpasses | 0.00% |
|  |  |  | B.2 - New Underpasses/Overpasses |  |
|  |  |  | (1) Foundation + Substructure: On completion of the foundation work including foundations for wing and return walls, abutments, piers up to the abutment/pier cap | 0.00% |
|  |  |  | (2) Super-structure: On completion of the super-structure in all respects including wearing coat, bearings, expansion joints, hand rails, crash barriers, road signs & markings, tests on completion etc. complete in all respect. Wearing Coat (a) in case of Overpass- wearing coat including expansion joints complete in all respects as specified and (b) in case of underpass- rigid pavement including drainage facility complete in all respects as specified as specified. | 0.00% |
|  |  |  | (3) Approaches: On completion of approaches including Retaining walls, stone pitching, protection works complete in all respect and fit for use. | 0.00% |
| 3 |  |  | A.1 - Widening and repairs of existing major bridges |  |
|  |  |  | (1) Foundation: | 0.00% |
|  |  |  | (2) Sub-structure: | 0.00% |
|  |  |  | (3) Super-structure: (including bearings.) | 0.00% |
|  |  |  | (4) Wearing Coat including expansion joints (5) Miscellaneous Items like hand rails, crash barrier, road markings etc. | 0.00% |
|  |  |  | (6) Wing walls/return walls | 0.00% |
|  |  |  | (7) Guide bunds, river training works etc. | 0.00% |
|  |  |  | (8) Approaches (including retaining walls, stone pitching, protection works). | 0.00% |
|  |  |  | A.2 - New major bridges |  |
|  |  |  | (1) Foundation: | 0.00% |
|  |  |  | (2) Sub-structure: | 0.00% |
|  |  |  | (3) Super-structure: (including bearings.) | 0.00% |
|  |  |  | (4) Wearing Coat including expansion joints | 0.00% |
|  |  |  | (5) Miscellaneous Items like hand rails, crash barrier, road markings etc. | 0.00% |
|  |  |  | (6) Wing walls/return walls | 0.00% |
|  |  |  | (7) Guide bunds, river training works etc. | 0.00% |
|  |  |  | (8) Approaches (including retaining walls, stone pitching, protection works). | 0.00% |
|  |  |  | B.1 - Widening and repairs of (a) ROB and (b) RUB |  |
|  |  |  | (1) Foundation | 0.00% |
|  |  |  | (2) Sub structure | 0.00% |
|  |  |  | (3) Superstructure (including bearing) | 0.00% |
|  |  |  | (4) wearing coat: (a) in case of ROB - wearing coat including expansion joints complete in all respects as specified and (b) in case of RUB - rigid pavement under RUB including drainage facility complete in all respect as specified. | 0.00% |
|  |  |  | (5) Miscellaneous items (like hand rails, crash barriers, road markings etc.) | 0.00% |
|  |  |  | (6) wing walls/return walls | 0.00% |
|  |  |  | (7) Approaches (including retaining walls, stone pitching, protection works). | 0.00% |
|  |  |  | B.2 - New ROB / RUB |  |
|  |  |  | (1) Foundation | 0.00% |
|  |  |  | (2) Sub structure | 0.00% |
|  |  |  | (3) Superstructure (including bearing) | 0.00% |
|  |  |  | (4) wearing coat: (a) in case of ROB - wearing coat including expansion joints complete in all respects as specified and (b) in case of RUB - rigid pavement under RUB including drainage facility complete in all respect as specified. | 0.00% |
|  |  |  | (5) Miscellaneous items (like hand rails, crash barriers, road markings etc.) | 0.00% |
|  |  |  | (6) wing walls/return walls | 0.00% |
|  |  |  | (7) Approaches (including Retaining walls/Reinforced Earth wall, stone pitching and protection works) | 0.00% |
|  |  |  | C.1 - Widening and repairs of Elevated section/Flyover/Grade Separators |  |
|  |  |  | (1) Foundation | 0.00% |
|  |  |  | (2) Sub structure | 0.00% |
|  |  |  | (3) Superstructure (including bearing) | 0.00% |
|  |  |  | (4) wearing coat including expansion joint | 0.00% |
|  |  |  | (5) Miscellaneous items (like hand rails, crash barriers, road markings etc.) | 0.00% |
|  |  |  | (6) wing walls/return walls | 0.00% |
|  |  |  | (7) Approaches (including Retaining walls/Reinforced Earth wall, stone pitching and protection works) | 0.00% |
|  |  |  | C.2 - New Elevated section/Flyover/Grade Separators |  |
|  |  |  | (1) Foundation: | 0.00% |
|  |  |  | (2) Sub-structure: | 0.00% |
|  |  |  | (3) Superstructure (including bearing) | 0.00% |
|  |  |  | (4) wearing coat including expansion joint | 0.00% |
|  |  |  | (5) Miscellaneous items (like hand rails, crash barriers, road markings etc.) | 0.00% |
|  |  |  | (6) wing walls/return walls | 0.00% |
|  |  |  | (7) Approaches (including Retaining walls/Reinforced Earth wall, stone pitching and protection works) | 0.00% |
| 4 | Other works |  | (i) Dismantling of Toll Plaza and existing pavement is all respect | 0.00% |
|  |  |  | (ii) Road side drains |  |
|  |  |  | (a) RCC covered drain / footpath | 0.00% |
|  |  |  | (iii) Road signs, markings (including transvers rumble strips), km stones, RCC crash barrier boundary pillar, , median, painting, safety devices, RPM, pedestrian guard rails, overhead traffic signs, median plantation etc. | 0.00% |
|  |  |  | (iv) Road side plantation | 0.00% |
|  |  |  | (v) Electrical works (street lights, shifting of high mast light, solar blinkers etc.) | 0.00% |
| 5 | Utility shifting |  | PHE | 0.00% |
|  |  |  | CSPDCL | 0.00% |
| Total |  | 100.00% |  | 100.00% |

#### 1.3	Procedure of estimating the value of work done.

#### 1.3.1	Road works

Procedure for estimating the value of road work done shall be as follows:

Table1.3.1

| Stage of Payment | Percentage -weight age | Payment Procedure |
| --- | --- | --- |
| A - Widening and strengthening of existing road |  |  |
| (1) Earthwork up to top of the sub- grade | 0.00% | Unit of measurement is linear length. Payment of each stage shall be made on pro rata basis on completion of a stage in a length of not less than 10 (ten) percent of the total length. |
| (2) Sub-base Course (GSB) | 0.00% |  |
| (3) Subbase | 0.00% |  |
| (4) Non bituminous Base course | 0.00% |  |
| (5) Bituminous Base course | 0.00% |  |
| (6) Wearing Coat | 0.00% |  |
| (7) widening and repair of culverts | 0.00% | Cost of completed culverts shall be determined pro rata basis with respect to the total no. of culverts. The payment shall be made on the completion of at least five culverts. |
| B.1 - Reconstruction realignment/bypass (Flexible pavement) | 0.00% | Unit of measurement is linear length. Payment of each stage shall be made on pro rata basis on completion of a stage in full length or 5(five) km. length, whichever is less. |
| (1) Earthwork up to top of the sub- grade | 0.00% |  |
| (2) Sub-base Course | 0.00% |  |
| (3) Non bituminous Base course | 0.00% |  |
| (4) Bituminous Base course | 0.00% |  |
| (5) Wearing Coat | 0.00% |  |
| B.2 - Reconstruction/ realignment/bypass RCC Crash Barrier (Rigid ) | 0.00% | Unit of measurement is linear length. Payment of each stage shall be made on pro rata basis on completion of a stage in full length or 2 km (Two) km. length, whichever is less. |
| (1) Earthwork up to top of the subgrade | 0.18% |  |
| (2)Plain Cement Concrete (PCC M-20) | 14.35% |  |
| (3) RCC Crash Barrier M-25 | 82.57% |  |
| (4) Reconstruction of RCC Crash Barrier M-25 |  |  |
| (5) Painting | 2.90% |  |
| C.1 - Reconstruction/ New Service Road (flexible Pavement) | 0.00% | Unit of measurement is linear length. Payment of each stage shall be made on pro rata basis on completion of a stage in full length or 5(five) km. length, whichever is less. |
| (1) Earthwork up to Sub grade top | 0.00% |  |
| (2) Sub base course (GSB) | 0.00% |  |
| (3) Non-bituminous base course (WMM) | 0.00% |  |
| (4) Bituminous base | 0.00% |  |
| (5) wearing coat | 0.00% |  |
| C.2 - Reconstruction/ New Service Road (Rigid Pavement) | 0.00% | Unit of measurement is linear length. Payment of each stage shall be made on pro rata basis on completion of a stage in full length or 5(five) km. length, whichever is less. |
| (1) Earthwork up to Sub grade top | 0.00% |  |
| (2) Sub base course (GSB) | 0.00% |  |
| (3) Dry lean concrete (DLC) | 0.00% |  |
| (4) Pavement quality concrete (PQC) course | 0.00% |  |
| D. - Reconstruction & New Culverts on existing road, realignments, bypasses | 0.00% | Cost of each culvert shall be determined on pro rata basis with respect to the total number of culverts. Payment shall be made on the completion of at least five culverts. |

@. For example, if the total length of bituminous work to be done is 100 km, the cost per km of bituminous work shall be determined as follows:

Cost per km = P x weightage for road work x weightage for bituminous work x (1/L)

Where P= Contract Price. And L = Total length in km.

Similarly, the rates per km for other stages shall be worked out accordingly.

Note: The length affected due to law-and-order problems or litigation during execution due to which the Contractor is unable to execute the work, may be deducted from the total project length for payment purposes. The total length calculated here is only for payment purposes and will not affect and referred in other clauses of the Contract Agreement.

#### 1.3.2	Minor Bridges and Underpasses/Overpasses.

Procedure for estimating the value of Minor Bridge and underpasses/Overpasses shall be as stated in table 1.3.2:

Table1.3.2

| Stage of Payment | Weight age | Payment Procedure |
| --- | --- | --- |
| A.1 - Widening and repairs of Minor Bridges |  | Cost of each minor bridge shall be determined on pro rata basis with respect to the total linear length of the minor bridges. Payment shall be made on the completion of widening & repair works of a minor bridge. |
| Widening of existing bridges | 0.00% |  |
| rehabilitation of existing bridges | 0.00% |  |
| A.2 - New of Minor Bridges |  |  |
| (1) Foundation + Substructure: On completion of the foundation work including foundations for wing and return walls, abutments, piers up to the abutment/pier cap | 0.00% | (i) Foundation +Sub-Structure: Cost of each minor bridge shall be determined on pro rata basis with respect to the total linear length (m) of the minor bridges. Payment against foundation + sub-structure shall be made on pro-rata basis on completion of a stage i.e. not less than 25% of the scope of foundation +sub-structure of each bridge subject to completion of at least two foundations along with sub-structure upto abutment/pier cap level of each bridge. In case where load testing is required for foundation, the trigger of first payment shall include load testing also where specified. |
| (2) Super-structure: On completion of the super-structure in all respects including wearing coat, bearings, expansion joints, hand rails, crash barriers, road signs & markings, tests on completion etc. complete in all respect. | 0.00% | (ii) Super-structure: Payment shall be made on pro-rata basis on completion of a stage i.e. completion of super-structure of at least one span in all respects as specified in the column of “Stage of Payment” in this sub-clause excluding any payment made in pursuance to here in under: If precast girders/segments are used, on casting of all such girders and segments for at least one span and on submission of Indemnity Bond by the Contractor, 40% of the actual cost of such precast girders/segments determined based on SoR prevalent on the Base date within 30 days of submission of the bill therefor. In case the Contract Price is lower/higher than the Estimated Project Cost as per RFP, then the SOR rates shall be reduced/ increased in the same proportion accordingly. Balance payment shall be after erection of / launching of these elements as per stage payment stipulations. |
| (3) Approaches: On completion of approaches including Retaining walls, stone pitching, protection works complete in all respect and fit for use. | 0.00% | (iii) Approaches: Payment shall be made on pro-rata basis on completion of a stage i.e. completion of approaches in all respect as specified in the column of “Stage of Payment” in this sub-clause. |
| (4) Guide Bunds and River Training Works: On completion of Guide Bunds and river training works complete in all respects | 0.00% | (iv) Guide Bunds and River Training Works: Payment shall be made on pro-rata basis on completion of a stage i.e. completion of Guide Bunds and River training Works in all respects as specified. |
| B.1 - Widening and repairs of Underpasses/Overpasses |  | Cost of each underpass/overpass shall be determined on pro rata basis with respect to the total linear length of the underpasses/overpasses. Payment shall be made on the completion of widening & repair works of a underpass / overpass. |
| B.2 - New Underpasses/Overpasses |  |  |
| (1) Foundation + Substructure: On completion of the foundation work including foundations for wing and return walls, abutments, piers up to the abutment/pier cap | 0.00% | (i) Foundation +Sub-Structure: Cost of each minor bridge shall be determined on pro rata basis with respect to the total linear length (m) of the minor bridges. Payment against foundation + sub-structure shall be made on pro-rata basis on completion of a stage i.e. not less than 25% of the scope of foundation +sub-structure of each bridge subject to completion of at least two foundations along with sub-structure upto abutment/pier cap level of each bridge. In case where load testing is required for foundation, the trigger of first payment shall include load testing also where specified. |
| (2) Super-structure: On completion of the super-structure in all respects including wearing coat, bearings, expansion joints, hand rails, crash barriers, road signs & markings, tests on completion etc. complete in all respect Wearing Coat (a) in case of Overpass- wearing coat including expansion joints complete in all respects as specified and (b) in case of underpass- rigid pavement including drainage facility complete in all respects as specified as specified. | 0.00% | (ii) Super-structure: Payment shall be made on pro-rata basis on completion of a stage i.e. completion of super-structure of at least one span in all respects as specified in the column of “Stage of Payment” in this sub-clause excluding any payment made in pursuance to here in under: If precast girders/segments are used, on casting of all such girders and segments for at least one span and on submission of Indemnity Bond by the Contractor, 40% of the actual cost of such precast girders/segments determined based on SoR prevalent on the Base date within 30 days of submission of the bill therefor. In case the Contract Price is lower/higher than the Estimated Project Cost as per RFP, then the SOR rates shall be reduced/ increased in the same proportion accordingly. Balance payment shall be after erection of / launching of these elements as per stage payment stipulations. |
| (3) Approaches: On completion of approaches including Retaining walls, stone pitching, protection works complete in all respect and fit for use. | 0.00% | (iii) Approaches: Payment shall be made on pro-rata basis on completion of a stage i.e. completion of approaches in all respect as specified in the column of “Stage of Payment” in this sub-clause excluding any payment made in pursuance to here in under: If Reinforced Earth Wall is used with Facia Panels/Blocks, on casting of all the Facia Panels/Blocks of all approaches and on submission of Indemnity Bond by the Contractor, 40% of the actual cost of such precast girders/segments determined based on SoR prevalent on the Base date within 30 days of submission of the bill therefor. In case the Contract Price is lower/higher than the Estimated Project Cost as per RFP, then the SOR rates shall be reduced/ increased in the same proportion accordingly. Balance payment shall be after erection of / launching of these elements as per stage payment stipulations. |

#### 1.3.3	Major Bridge works, ROB/RUB and Structures

Procedure for estimating the value of major Bridge works, ROB/RUB and structure work shall be as stated in table 1.3.3

Table 1.3.3

| Stage of payment | Weight age | Payment procedure |
| --- | --- | --- |
| A.1 - Widening and repairs of existing major bridges |  |  |
| (1) Foundation: | 0.00% | (i) Foundation: Cost of each Major Bridge shall be determined on pro rata basis with respect to the total linear length (m) of the Major Bridge. Payment against foundation shall be made on pro-rata basis on completion of a stage i.e. not less than 25% of the scope of foundation of the major Bridge subject to completion of atleast two foundations of the major Bridge .In case where load testing is required for foundation, the trigger of first payment shall include load testing also where specified. |
| (2) Sub-structure: | 0.00% | Payment against Substructure shall be made on pro-rata basis on completion of a stage i.e. not less than 25% of the scope of sub- structure of the major bridge subject to completion of at least two sub-structures of abutments/piers up to abutment/pier cap level of the major bridge. |
| (3) Super-structure: (including bearings.) | 0.00% | Super-structure: Payment shall be made on pro-rata basis on completion of a stage i.e. completion of super- structure including bearings of at least one span in all respects as specified excluding any payment made in pursuance to here in under: If precast girders/ segments are used, on casting of all such girders and segments for at least one span and on submission of Indemnity Bond by the Contractor, 40% of the actual cost of such precast girders/segments determined based on SoR prevalent on the Base date within 30 days of submission of the bill therefor. In case the Contract Price is lower/ higher than the Estimated Project Cost as per RFP, then the SOR rates shall be reduced/increased in the same proportion accordingly. Balance payment shall be after erection of / launching of these elements as per stage payment stipulations. |
| (4) Wearing Coat including expansion joints (5) Miscellaneous Items like hand rails, crash barrier, road markings etc. | 0.00% | Wearing Coat: Payment shall be made on completion of wearing coat including expansion joints complete in all respects as specified. Miscellaneous: Payments shall be made on completion of all miscellaneous works like hand rails, crash barriers, road markings etc. complete in all respects as specified. |
| (6) Wing walls/return walls | 0.00% | Wing walls/return walls: Payments shall be made on completion of all wing walls/return walls complete in all respects as specified. |
| (7) Guide bunds, River Training works etc. | 0.00% | Guide Bunds, River Training works: Payments shall be made on completion of all guide bunds/river training works etc. complete in all respects as specified. |
| (8) Approaches (including Retaining walls, stone pitching and protection works) | 0.00% | Approaches: Payments shall be made on completion of both approaches including stone pitching, protection works, etc. complete in all respects as specified. |
| A.2 - New major bridges |  |  |
| (1) Foundation: | 0.00% | Foundation: Cost of each Major Bridge shall be determined on pro rata basis with respect to the total linear length (m) of the Major Bridge. Payment against foundation shall be made on pro-rata basis on completion of a stage i.e. not less than 25% of the scope of foundation of the major Bridge subject to completion of at least two foundations of the major bridge. In case where load testing is required for foundation, the trigger of first payment shall include load testing also where specified. |
| (2) Sub-structure: | 0.00% | Payment against Substructure shall be made on pro-rata basis on completion of a stage i.e. Not less than 25% of the scope of sub- structure of the major bridge subject to completion of at least two sub-structures of abutments/piers up to abutment/pier cap level of the major bridge. |
| (3) Super-structure: (including bearings.) | 0.00% | Super-structure: Payment shall be made on pro-rata basis on completion of a stage i.e., completion of super- structure including bearings of at least one span in all respects as specified excluding any payment made in pursuance to here in under: If precast girders/segments are used, on casting of all such girders and segments for at least one span and on submission of Indemnity Bond by the Contractor, 40% of the actual cost of such precast girders/segments determined based on SoR prevalent on the Base date within 30 days of submission of the bill therefor. In case the Contract Price is Iower/ higher than the Estimated Project Cost as per RFP, then the SOR rates shall be reduced/ increased in the same proportion accordingly. Balance payment shall be after erection of / launching of these elements as per stage payment stipulations. |
| (4) Wearing Coat including expansion joints | 0.00% | Wearing Coat: Payment shall be made on completion of wearing coat including expansion joints complete in all respects as specified. |
| (5) Miscellaneous Items like hand rails, crash barrier, road markings etc. | 0.00% | Miscellaneous: Payments shall be made on completion of all miscellaneous works like hand rails, crash barriers, road markings etc. complete in all respects as specified. |
| (6) Wing walls/return walls | 0.00% | Wing walls/return walls: Payments shall be made on completion of all wing walls/return walls complete in all respects as specified. |
| (7) Guide bunds, River Training works etc. | 0.00% | Guide Bunds, River Training works: Payments shall be made on completion of all guide bunds/river training works etc. complete in all respects as specified. |
| (8) Approaches (including Retaining walls, stone pitching and protection works) | 0.00% | Approaches: Payments shall be made on completion of both approaches including stone pitching, protection works, etc. complete in all respects as specified. |
| B.1 - Widening and repairs of (a) ROB and (b) RUB |  |  |
| (1) Foundation | 0.00% | Foundation: Cost of each ROB/RUB shall be determined on pro rata basis with respect to the total linear length (m) of the ROB/RUB. Payment against foundation shall be made on pro-rata basis on completion of a stage i.e. not less than 25% of the scope of foundation of the ROB/RUB subject to completion of at least two foundations of the ROB/RUB In case where load testing is required for foundation, the trigger of first payment shall include load testing also where specified. |
| (2) Sub-structure | 0.00% | Sub-structure: Payment against sub- structure shall be made on pro-rata basis on completion of a stage i.e. not less than 25% of the scope of sub- structure of ROB/RUB subject to completion of at least two sub-structures of abutments/piers up to abutment/pier cap level of the ROB/RUB. |
| (3) Super-structure (including bearing) | 0.00% | Super-structure: Payment shall be made on pro-rata basis on completion of a stage i.e. completion of super- structure including bearings of at least one span in all respects as specified excluding any payment made in pursuance to here in under: If precast girders/segments are used, on casting of all such girders and segments for at least one span and on submission of Indemnity Bond by the Contractor, 40% of the actual cost of such precast girders/segments determined based on SoR prevalent on the Base date within 30 days of submission of the bill therefor. In case the Contract Price is Iower/ higher than the Estimated Project Cost as per RFP, then the SOR rates shall be reduced/ increased in the same proportion accordingly. Balance payment shall be after erection of / launching of these elements as per stage payment stipulations. |
| (4) Wearing Coat including expansion joints in case of ROB. In case of RUB-rigid pavement under RUB including drainage facility as specified | 0.00% | Wearing Coat: Payment shall be made on completion of (a) in case of ROB- wearing coat including expansion joints complete in all respects as specified and (b) in case of RUB-rigid pavement under RUB including drainage facility complete in all respects as specified. |
| (5) Miscellaneous Items like hand rails, crash barrier, road markings etc. | 0.00% | Miscellaneous: Payments shall be made on completion of all miscellaneous works like hand rails, crash barriers, road markings etc. complete in all respects as specified. |
| (6) Wing walls/return walls | 0.00% | Wing walls/return walls: Payments shall be made on completion of all wing walls/return walls complete in all respects as specified. |
| (7) Approaches (including retaining walls, stone pitching, protection works). | 0.00% | Approaches: Payments shall be made on completion of both approaches including stone pitching, protection works, etc. complete in all respects as specified |
| B.2 - New ROB / RUB |  |  |
| (1) Foundation | 0.00% | (i) Foundation: Cost of each Major Bridge shall be determined on pro rata basis with respect to the total linear length (m) of the Major Bridge. Payment against foundation shall be made on pro-rata basis on completion of a stage i.e. not less than 25% of the scope of foundation of the major Bridge subject to completion of atleast two foundations of the major Bridge .In case where load testing is required for foundation, the trigger of first payment shall include load testing also where specified. |
| (2) Sub-structure | 0.00% | (ii) Sub-Structure:. Payment against Sub-structure shall be made on pro-rata basis on completion of a stage i.e. not less than 25% of the scope of sub-structure of the major bridge subject to completion of at least two sub-structures of abutments/piers upto abutment/pier cap level of the major bridge. |
| (3) Super-structure (including bearing) | 0.00% | (iii) Super-structure: Payment shall be made on pro-rata basis on completion of a stage i.e. completion of super-structure including bearings of atleast one span in all respects as specified excluding any payment made in pursuance to here in under: If precast girders/segments are used, on casting of all such girders and segments for at least one span and on submission of Indemnity Bond by the Contractor, 40% of the actual cost of such precast girders/segments determined based on SoR prevalent on the Base date within 30 days of submission of the bill therefor. In case the Contract Price is Iower/ higher than the Estimated Project Cost as per RFP, then the SOR rates shall be reduced/ increased in the same proportion accordingly. Balance payment shall be after erection of / launching of these elements as per stage payment stipulations. |
| (4) Wearing Coat including expansion joints in case of ROB. In case of RUB-rigid pavement under RUB including drainage facility as specified | 0.00% | (iv) Wearing Coat: Payment shall be made on completion of wearing coat including expansion joints complete in all respects as specified. |
| (5) Miscellaneous Items like hand rails, crash barrier, road markings etc. | 0.00% | (v) Miscellaneous: Payments shall be made on completion of all miscellaneous works like hand rails, crash barriers, road markings etc. complete in all respects as specified. |
| (6) Wing walls/return walls | 0.00% | (vi) Wing walls/return walls: Payments shall be made on completion of all wing walls/return walls complete in all respects as specified. |
| (7) Approaches (including Retaining walls /Reinforced Earth wall, stone pitching and protection works) | 0.00% | (vii)Approaches: Payments shall be made on completion of both approaches including stone pitching, protection works, etc. complete in all respects as specified excluding any payment made in pursuance to here in under: If Reinforced Earth Wall IS used with Facia Panels/Blocks, on casting of all the Facia Panels/Blocks of all approaches and on submission oflndemnity Bond by the Contractor, 40% of the actual cost of such precast girders/segments determined based on SoR prevalent on the Base date within 30 days of submission of the bill therefor. In case the Contract Price is lower! higher than the Estimated Project Cost as per RFP, then the SOR rates shall be reduced/ increased in the same proportion accordingly. Balance payment shall be after erection of / launching of these elements as per stage payment stipulations. |
| C.1 - Widening and repairs of Elevated section/Flyover/Grade Separators |  |  |
| (1) Foundation | 0.00% | Foundation: Cost of each structure shall be determined on pro rata basis with respect to the total linear length (m) of the structure. Payment against foundation shall be made on pro-rata basis on completion of a stage i.e. not less than 25% of the scope of foundation of the structure. subject to completion of at least two foundations of the Structure. In case where load testing is required for foundation, the trigger of first payment shall include load testing also where specified. |
| (2) Sub-structure | 0.00% | Sub-structure: Payment against sub- structure shall be made on pro-rata basis on completion of a stage i.e. not less than 25% of the scope of sub- structure of structure subject to completion of at least two sub-structures of abutments/piers up to abutment/pier cap level of the structure. |
| (3) Super-structure (including bearing) | 0.00% | Super-structure: Payment shall be made on pro-rata basis on completion of a stage i.e. completion of super- structure including bearings of at least one span in all respects as specified excluding any payment made in pursuance to here in under: If precast girders/segments are used, on casting of all such girders and segments for at least one span and on submission of Indemnity Bond by the Contractor, 40% of the actual cost of such precast girders/segments determined based on SoR prevalent on the Base date within 30 days of submission of the bill therefor. In case the Contract Price is Iower/ higher than the Estimated Project Cost as per RFP, then the SOR rates shall be reduced/ increased in the same proportion accordingly. Balance payment shall be after erection of / launching of these elements as per stage payment stipulations. |
| (4) Wearing Coat including expansion joints | 0.00% | Wearing Coat: Payment shall be made on completion of wearing coat including expansion joints complete in all respects as specified. |
| (5) Miscellaneous Items like hand rails, crash barrier, road markings etc. | 0.00% | Miscellaneous: Payments shall be made on completion of all miscellaneous works like hand rails, crash barriers, road markings etc. complete in all respects as specified. |
| (6) Wing walls/return walls | 0.00% | Wing walls/return walls: Payments shall be made on completion of all wing walls/return walls complete in all respects as specified. |
| (7) Approaches (including Retaining walls/Reinforced Earth wall, stone pitching and protection works) | 0.00% | Approaches: Payments shall be made on completion of both approaches including stone pitching, protection works, etc. complete in all respects as specified excluding any payment made in pursuance to here in under: If Reinforced Earth Wall IS used with Facia Panels/Blocks, on casting of all the Facia Panels/Blocks of all approaches and on submission oflndemnity Bond by the Contractor, 40% of the actual cost of such precast girders/segments determined based on SoR prevalent on the Base date within 30 days of submission of the bill therefor. In case the Contract Price is lower! higher than the Estimated Project Cost as per RFP, then the SOR rates shall be reduced/ increased in the same proportion accordingly. Balance payment shall be after erection of / launching of these elements as per stage payment stipulations. |
| C.2 - New Elevated section/Flyover/Grade Separators |  |  |
| (1) Foundation | 0.00% | Foundation: Cost of each structure shall be determined on pro rata basis with respect to the total linear length (m) of the structure. Payment against foundation shall be made on pro-rata basis on completion of a stage i.e. not less than 25% of the scope of foundation of the structure. subject to completion of at least two foundations of the Structure. In case where load testing is required for foundation, the trigger of first payment shall include load testing also where specified. |
| (2) Sub-structure | 0.00% | Sub-structure: Payment against sub- structure shall be made on pro-rata basis on completion of a stage i.e. not less than 25% of the scope of sub- structure of structure subject to completion of at least two sub-structures of abutments/piers up to abutment/pier cap level of the structure. |
| (3) Super-structure (including bearing) | 0.00% | Super-structure: Payment shall be made on pro-rata basis on completion of a stage i.e. completion of super- structure including bearings of at least one span in all respects as specified excluding any payment made in pursuance to here in under: If precast girders/segments are used, on casting of all such girders and segments for at least one span and on submission of Indemnity Bond by the Contractor, 40% of the actual cost of such precast girders/segments determined based on SoR prevalent on the Base date within 30 days of submission of the bill therefor. In case the Contract Price is Iower/ higher than the Estimated Project Cost as per RFP, then the SOR rates shall be reduced/ increased in the same proportion accordingly. Balance payment shall be after erection of / launching of these elements as per stage payment stipulations. |
| (4) Wearing Coat including expansion joints | 0.00% | Wearing Coat: Payment shall be made on completion of wearing coat including expansion joints complete in all respects as specified. |
| (5) Miscellaneous Items like hand rails, crash barrier, road markings etc. | 0.00% | Miscellaneous: Payments shall be made on completion of all miscellaneous works like hand rails, crash barriers, road markings etc. complete in all respects as specified. |
| (6) Wing walls/return walls | 0.00% | Wing walls/return walls: Payments shall be made on completion of all wing walls/return walls complete in all respects as specified. |
| (7) Approaches (including Retaining walls/Reinforced Earth wall, stone pitching and protection works) | 0.00% | Approaches: Payments shall be made on completion of both approaches including stone pitching, protection works, etc. complete in all respects as specified excluding any payment made in pursuance to here in under: If Reinforced Earth Wall is used with Facia Panels/Blocks, on casting of all the Facia Panels/Blocks of all approaches and on submission ofIndemnity Bond by the Contractor, 40% of the actual cost of such precast girders/segments determined based on SoR prevalent on the Base date within 30 days of submission of the bill therefor. In case the Contract Price is lower/ higher than the Estimated Project Cost as per RFP, then the SOR rates shall be reduced/ increased in the same proportion accordingly. Balance payment shall be after erection of / launching of these elements as per stage payment stipulations. |

#### 1.3.4	Other works.

Procedure for estimating the value of other works done shall be as stated in table 1.3.4:

Table 1.3.4

| Stage of Payment | Weight age | Payment Procedure |
| --- | --- | --- |
| (i) Dismantling of Toll Plaza and existing pavement is all respect | 0.00% | Payment shall be made on pro rata basis for completed work. |
| (ii) Road side drains |  | Unit of measurement is linear length in km. Payment shall be made on pro rata basis on completion of a stage in a length of not less than 25 % (ten per cent) of the total length. |
| (a) RCC covered drain / footpath | 0.00% |  |
| (iii) Road signs, markings (including transvers rumble strips), RCC crash barrier km stones, boundary pillar,, median, painting, safety devices, RPM, pedestrian guard rails, overhead traffic signs, median plantation etc. | 0.00% | Payment shall be made on pro rata basis for completed facilities. |
| (iv) Road side plantation | 0.00% | Payment shall be made on pro rata basis for completed facilities. |
| (v) Electrical works (street lights, shifting of high mast light, solar blinkers etc.) | 0.00% | Payment shall be made on pro rata basis for completed facilities. |

#### 1.3.5	Utility Shifting

Procedure for estimating the value of utility shifting works done shall be as stated in Table 1.3.5:

#### Table 1.3.5

| Stage of Payment | Weight age | Payment procedure |
| --- | --- | --- |
| PHE | 0.00% | Payment is divided in following activities and Payment of each activity shall be made on pro rata basis on completion of 5km of linear project length. Removal of existing utility; 30%. Erection/ Laying; 30%. Commissioning; 40%. Dismantling will include proper listing and stocking of usable and non-usable items. Commissioning will be completed on furnishing the commissioning certificate from concerned utility owning department. |
| CSPDCL | 0.00 % |  |

#### 2.	Procedure for payment for Maintenance.

#### 2.1	The cost for maintenance shall be as stated in Clause 14.1.(i)

#### 2.2	Payment for Maintenance shall be made in quarterly installments in accordance with the provisions of Clause 19.7.

Schedule-I

(See Clause 10.2.4)

DRAWINGS

- Drawings

In compliance of the obligations set forth in Clause 10.2 of this Agreement, the Contractor shall furnish to the Authority’s Engineer, free of cost, all Drawings listed in Annex-I of this Schedule-I.

- Additional Drawings

If the Authority’s Engineer determines that for discharging its duties and functions under this Agreement, it requires any drawings other than those listed in Annex-I, it may by notice require the Contractor to prepare and furnish such drawings forthwith.  Upon receiving a requisition to this effect, the Contractor shall promptly prepare and furnish such drawings to the Authority’s Engineer, as if such drawings formed part of Annex-I of this Schedule-I.

Annex-I

(Schedule-I)

List of Drawings

[Note: The Authority shall describe in this Annex-I, all the Drawings that the Contractor is required to furnish under Clause 10.2.]

A minimum list of the drawings of the various components / elements of the Project Highway and project facilities required to be submitted by the Contractors given below:

- Drawings of horizontal alignment, vertical profile and detailed cross sections..

- Drawings of cross-drainage works.

- Drawings of Major/Minor intersections, Grade Separated all type of Structures.

- Drawing of road furniture including traffic signage, marking, safety barriers etc.

- Drawing of traffic diversion plan.

- Drawing of street lighting.

- Drawing as per instruction of Authority’s Engineer.

- General arrangement showing area of base camp and administrative block.

Schedule-J

(See Clause 10.3.2)

PROJECT COMPLETION SCHEDULE

1.	Project Completion Schedule

During Construction period, the Contractor shall comply with the requirements set forth in this Schedule J for each of the Project Milestones and the Scheduled Completion Date (180 days).  Within 15 (fifteen) days of the date of each Project Milestone, the Contractor shall notify the Authority of such compliance along with necessary particulars thereof.

2.	Project Milestone-I

(i)	Project Milestone-I shall occur on the date falling on the 63rd (Sixty Three) day from the Appointed Date (the “Project Milestone-I”).

(ii)	Prior to the occurrence of Project Milestone-I, the Contractor shall have commenced construction of the Project Highway and submitted to the Authority duly and validly prepared Stage Payment Statements completion schedule in reference to Schedule-H Items, Stages and Sub-stages payment statements for an amount not less than 10% (ten per cent) of the Contract Price.

3.	Project Milestone-II

(i)        Project Milestone-II shall occur on the date falling on the 108th (One  Hundred and Eight) day from the Appointment Date (the “Project Milestone-II”).

(ii)	Prior to the occurrence of Project Milestone-II, the Contractor shall have continued with construction of the Project Highway and submitted to the Authority duly and validly prepared Stage Payment Statements  for an amount not less than 35% (thirty five per cent) of the Contract Price and should have started construction of all bridges.

4.	Project Milestone-III

(i)	Project Milestone-III shall occur on the date falling on the 153rd  (One Hundred Fifty Three ) day from the Appointed Date (the “Project Milestone-III”).

(ii)	Prior to the occurrence of Project Milestone-III, the Contractor shall have continued with construction of the Project Highway and submitted to the Authority duly and validly prepared Stage Payment Statements for an   amount not less than 70% (seventy percent) of the Contract Price. and should have started construction of all project facilities.

5.	Schedule Completion Date

(i)	The Schedule Completion Date shall occur on the 180th (Two Hundred & Eighty)  day from the Appointed Date.

(ii)	On or before the Scheduled Completion Date, the Contractor shall have completed construction in accordance with this Agreement.

6.	Extension of Time

Upon extension of any or all of the aforesaid Project Milestones or the Scheduled Completion Date, as the case may be, under and in accordance with the provisions of this Agreement, the Project Completion Schedule shall be deemed to have been amended accordingly.

Schedule – K

(See Clause 12.1 (ii))

Tests on Completion

1. 	Schedule for Tests

(i) 	The Contractor shall, no later than 30 (thirty) days prior to the likely completion of construction, notify the Authority’s Engineer and the Authority of its intent to subject the  Project Highway to Tests, and no later than 10 (ten) days prior to the actual date of Tests, furnish to the Authority’s Engineer and the Authority detailed inventory and particulars of all works and equipment forming part of Works.

(ii)	The Contractor shall notify the Authority’s Engineer of its readiness to subject the Project Highway to Tests at any time after 10 (ten) days from the date of such notice, and  pon receipt of such notice, the Authority’s Engineer shall, in consultation with the Contractor, determine the date and time for each Test and notify the same to the Authority who may designate its representative to witness the Tests. The Authority’s Engineer shall thereupon conduct the Tests itself or cause any of the Tests to be conducted in accordance with Article 12 and this Schedule-K.

2. 	Tests

(i)	Visual and physical test: The Contractor shall conduct  a visual and physical check of construction to determine that all works and equipment forming part thereof conform to the provisions of this Agreement in the presence of Authority Engineer. The physical tests shall include all tests as per instruction of Authority Engineer.

(ii) 	Riding quality test: Riding quality of each lane of the carriageway shall be checked with the help of a Network Survey Vehicle (NSV) fitted with latest equipments and the maximum permissible roughness for purposes of this Test shall be [2,000 (two thousand)] mm for each kilometre.

(iii) 	Tests for bridges: All major and minor bridges shall be subjected to the rebound hammer and ultrasonic pulse velocity tests, to be conducted in accordance with the rocedure described in Special Report No. 17: 1996 of the IRC Highway Research Board on Nondestructive Testing Techniques, at two spots in every span, to be chosen at random by the Authority’s Engineer. Bridges with a span of 15 (fifteen) metres or more shall also be subjected to load testing.

(iv) 	Other tests: The Authority’s Engineer may require the Contractor to carry out or cause to be carried additional tests, in accordance with Good Industry Practice, for determining the compliance of the Project Highway with Specifications and Standards, except tests as specified in clause 5,but shall include measuring the reflectivity of road markings and road signs; and measuring the illumination level (lux) of lighting using requisite testing equipment.

(v) 	Environmental audit: The Authority’s Engineer shall carry out a check to determine conformity of the Project Highway with the environmental requirements set forth in Applicable Laws and Applicable Permits.

(vi)	 Safety Audit: The Authority’s Engineer shall carry out, or cause to be carried out, a safety audit to determine conformity of the Project Highway with the safety requirements and Good Industry Practice.

3.	 Agency for conducting Tests

All Tests set forth in this Schedule-K shall be conducted by the Authority’s Engineer or such other agency or person as it may specify in consultation with the Authority.

4. 	Completion Certificate

Upon successful completion of Tests, the Authority’s Engineer shall issue the Completion Certificate in accordance with the provisions of Article 12.

5. 	The Authority Engineer will carry out tests with following equipment at his own cost in the presence of contractor’s representative.

| Sr. No. | Key metrics of Asset | Equipment to be used | Frequency of condition survey |
| --- | --- | --- | --- |
| 1 | Surface defects of pavement | Network Survey Vehicle (NSV) | At least twice a year (As per survey months defined for the state basis rainy season) |
| 2 | Roughness of pavement | Network Survey Vehicle (NSV) | At least twice a year (As per survey months defined for the state basis rainy season) |
| 3 | Strength of Pavement | Falling Weight Deflectometer (FWD) | At least once a year |
| 4 | Bridges | Mobile Bridge Inspection Unit (MBU) | At least twice a year (As per survey months defined for the state basis rainy season) |
| 5 | Road signs | Retro-reflectometer | At least twice a year (As per survey months defined for the state basis rainy season) |

The first testing with the help of NSV shall be conducted at the time of issue of

Completion Certificate.

Schedule-L

(See Clause 12.2 and 12.4)

COMPLETION CERTIFICATE

1	I/,……………(NameoftheAuthority Engineer),actingasAuthorityEngineer,underandinaccordancewiththe Agreement Dated……………(the“Agreement”), for the’Construction Of Rcc Crash Barrier Between  Main Carriageway And Service Road In    Km.281.600 To Km. 307.600,  Of N.H. 53 (Old N.H.06) In Chhattishgarh State Under Road Safty Work

NameofContractor),herebycertifythattheTestsin accordance with Article12oftheAgreementhavebeen successfully undertakentodeterminecomplianceoftheProject Highway withtheprovisionsoftheAgreement,andIamsatisfiedthattheProject Highway canbesafelyandreliablyplacedinserviceoftheUsers thereof.

2	Itiscertifiedthat,intermsoftheaforesaidAgreement,allworksformingpartoftheProject Highwayhavebeencompleted, andtheProjectHighwayisherebydeclaredfitforentryintooperationonthis the ______day of___	20__

SIGNED, SEALED AND DELIVERED

For and on behalf of

Authority’s Engineer by:

(Signature)

(Name)

(Designation)

(Address)

Schedule – M

(See Clauses 14.6, 15.2 and 19.7)

Payment Reduction for Non-Compliance

1. Payment reduction for non-compliance with the Maintenance Requirements

(i) 	Monthly lump sum payments for maintenance shall be reduced in the case of noncompliance with the Maintenance Requirements set forth in Schedule-E.

(ii) 	Any deduction made on account of non-compliance with the Maintenance Requirements shall not be paid even after compliance subsequently. The deductionsshall continue to be made every month until compliance is done.

(iii) 	The Authority’s Engineer shall calculate the amount of payment reduction on the basis of weightage in percentage assigned to non-conforming items as given in Paragraph 2.

- Percentage reductions in lump sum payments on monthly basis

(i) 	The following percentages shall govern the payment reduction:

| S. No. | Item/Defect/Deficiency | Percentage |
| --- | --- | --- |
| (a) | Carriageway/Pavement |  |
| (i) | Potholes, cracks, other surface defects | 15% |
| (ii) | Repairs of Edges, Rutting | 5% |
| (b) | Road, Embankment, Cuttings, Shoulders |  |
| (i) | Edge drop, inadequate cross fall, undulations, settlement, potholes, ponding, obstructions | 10% |
| (ii) | Deficient slopes, raincuts, disturbed pitching, vegetation growth, pruning of trees | 5% |
| (c) | Bridges and Culverts |  |
| (i) | Desilting, cleaning. vegetation growth, damaged pitching, flooring, parapets, wearing course, footpaths, any damage to foundations | 20% |
| (ii) | Any Defects in superstructures, bearings and sub-structures | 10% |
| (iii) | Painting, repairs/replacement kerbs, railings, parapets,guideposts/crash barriers | 5% |
| (d) | Road side Drains |  |
| (i) | Cleaning and repair of drains | 5% |
| (e) | Road Furniture |  |
| (i) | Cleaning, painting, replacement of road signs, delineators, road markings, 200 m/km/5th km stones | 5% |
| (f) | Miscellaneous Items |  |
| (i) | Removal of dead animals, broken down/accidented vehicles, fallen trees, road blockades or malfunctioning of mobile crane | 10% |
| (ii) | Any other Defects in accordance with paragraph 1. | 5% |
| (g) | Defects in Other Project Facilities | 5% |

(ii)	 The amount to be deducted from monthly lump-sum payment for non- compliance of

particular item shall be calculated as under:

Where,

P= 	Percentage of particular item/Defect/deficiency for deduction

M1= 	Monthly lump-sum payment in accordance para 1.2 above of this Schedule

M2= 	Monthly lump-sum payment in accordance para 1.2 above of this Schedule

L1= 	Non-complying length L = Total length of the road,

R= 	Reduction (the amount to be deducted for non-compliance for a particular

item/Defect/deficiency

The total amount of reduction shall be arrived at by summation of reductions for such

items/Defects/deficiency or non-compliance.

For any Defect in a part of one kilometer, the non-conforming length shall be taken as one kilometer.

Schedule – N

(See Clause 18.1 (i))

Selection of Authority’s Engineer

1. 	Selection of Authority’s Engineer

(i) 	The provisions of the Model Request for Proposal for Selection of Technical Consultants, issued by the Ministry of Finance in May 2009, or any substitute thereof shall apply for selection of an experienced firm to discharge the functions and duties of an Authority’s Engineer.

(ii) 	In the event of termination of the Technical Consultants appointed in accordance with the provisions of Paragraph 1.1, the Authority shall appoint another firm of Technical Consultants forthwith and may engage a government-owned entity in accordance with the provisions of Paragraph 3 of this Schedule-N.

2. 	Terms of Reference

The Terms of Reference for the Authority’s Engineer (the “TOR”) shall substantially conform with Annex 1 to this Schedule N.

3.	Appointment of Government entity as Authority’s Engineer

Notwithstanding anything to the contrary contained in this Schedule, the Authority may in its discretion appoint a government-owned entity as the Authority’s Engineer; provided that such entity shall be a body corporate having as one of its primary functions the provision of consulting, advisory and supervisory services for engineering projects; provided further that  government-owned entity which is owned or controlled by the Authority shall not be eligible for appointment as Authority’s Engineer.

Annex – I

(Schedule - N)

Annex-I :Terms of Reference for Authority’s Engineer

1. 	Scope

(i) 	These Terms of Reference (the “TOR”) for the Authority’s Engineer are being specified pursuant to the EPC Agreement dated ........... (the “Agreement), which has been entered into between the [name and address of the Authority] (the “Authority”) and .......... (the “Contractor”)#‘ Construction Of Rcc Crash Barrier Between  Main Carriageway And Service Road In    Km.281.600 To Km. 307.600,  Of N.H. 53 (Old N.H.06) In Chhattishgarh State Under Road Safty Work

, and a copy of which is annexed hereto and marked as Annex-A to form part of this TOR.

# - In case the bid of Authority’s Engineer is invited simultaneously with the bid of EPC project, then the status of bidding of EPC project only to be indicated

(ii) 	The TOR shall apply to construction and maintenance of the Project Highway.

2. 	Definitions and interpretation

(i) 	The words and expressions beginning with or in capital letters and not defined hereinbut defined in the Agreement shall have, unless repugnant to the context, the meaning respectively assigned to them in the Agreement.

(ii) 	References to Articles, Clauses and Schedules in this TOR shall, except where the context otherwise requires, be deemed to be references to the Articles, Clauses and Schedules of the Agreement, and references to Paragraphs shall be deemed to be references to Paragraphs of this TOR.

(iii) 	The rules of interpretation stated in Article 1 of the Agreement shall apply, mutatismutandis, to this TOR.

3. 	General

(i) 	The Authority’s Engineer shall discharge its duties in a fair, impartial and efficient manner, consistent with the highest standards of professional integrity and Good Industry Practice.

(ii) 	The Authority’s Engineer shall perform the duties and exercise the authority in accordance with the provisions of this Agreement, but subject to obtaining prior written approval of the Authority before determining:

(a) 	any Time Extension;

(b) 	any additional cost to be paid by the Authority to the Contractor;

(c) 	the Termination Payment; or

(d) 	issuance of Completion Certificate or

(e) 	any other matter which is not specified in (a), (b), (c) or (d) above and whichcreates a financial liability on either Party.

(iii) 	The Authority’s Engineer shall submit regular periodic reports, at least once every month, to the Authority in respect of its duties and functions under this Agreement. Such reports shall be submitted by the Authority’s Engineer within 10 (ten) days of the beginning of every month.

(iv) 	The Authority’s Engineer shall inform the Contractor of any delegation of its duties and responsibilities to its suitably qualified and experienced personnel; provided, however, that it shall not delegate the authority to refer any matter for the Authority’s prior approval in accordance with the provisions of Clause 18.2.

(v) 	The Authority’s Engineer shall aid and advise the Authority on any proposal for Change of Scope under Article 13.

(vi) 	In the event of any disagreement between the Parties regarding the meaning, scope and nature of Good Industry Practice, as set forth in any provision of the Agreement, the Authority’s Engineer shall specify such meaning, scope and nature by issuing a reasoned written statement relying on good industry practice and authentic literature.

4. 	Construction Period

(i) 	During the Construction Period, the Authority’s Engineer shall review and approve the Drawings furnished by the Contractor along with supporting data, including the geo-technical and hydrological investigations, characteristics of materials from borrow areas and quarry sites, topographical surveys, and the recommendations of the Safety Consultant in accordance with the provisions of Clause 10.1 (vi). The Authority’s Engineer shall complete such review and approval and send its observations to the Authority and the Contractor within 15 (fifteen) days of receipt of such Drawings; provided, however that in case of a Major Bridge or Structure, the aforesaid period of 15 (fifteen) days may be extended upto 30 (thirty) days. In particular, such comments shall specify the conformity or otherwise of such Drawings with the Scope of the Project and Specifications and Standards.

(ii) 	The Authority’s Engineer shall review and approve any revised Drawings sent to it by the Contractor and furnish its comments within 10 (ten) days of receiving such Drawings.

(iii) 	The Authority’s Engineer shall review and approve the Quality Assurance Plan submitted by the Contractor and shall convey its comments to the Contractor within a period of 21 (twenty one) days stating the modifications, if any, required thereto.

(iv) 	The Authority’s Engineer shall complete the review and approve of the methodology proposed to be adopted by the Contractor for executing the Works, and convey its comments to the Contractor within a period of 10 (ten) days from the date of receipt of the proposed methodology from the Contractor.

(v) 	The Authority’s Engineer shall grant written approval to the Contractor, where necessary, for interruption and diversion of the flow of traffic in the existing lane(s) of the Project Highway for purposes of maintenance during the Construction Period in accordance with the provisions of Clause 10.4.

(vi) 	The Authority’s Engineer shall review the monthly progress report furnished by the Contractor and send its comments thereon to the Authority and the Contractor within 7 (seven) days of receipt of such report.

(vii) 	The Authority’s Engineer shall inspect the Construction Works and the Project Highway and shall submit a monthly Inspection Report bringing out the results of inspections and the remedial action taken by the Contractor in respect of Defects or deficiencies. In particular, the Authority’s Engineer shall include in its Inspection Report, the compliance of the recommendations made by the Safety Consultant.

- The Authority’s Engineer shall conduct the pre-construction review ofmanufacturer'stest reports and standard samples of manufactured Materials, and such other Materials as the Authority’s Engineer may require.

- For determining that the Works conform to Specifications and Standards, the Authority’s Engineer shall require the Contractor to carry out, or cause to be carried out, tests at such time and frequency and in such manner as specified in the Agreement and in accordance with Good Industry Practice for quality assurance. For purposes of this Paragraph 4 (ix), the tests specified in the IRC Special Publication-11 (Handbook of Quality Control for Construction of Roads and Runways) and the Specifications for Road and Bridge Works issued by MORTH (the “Quality Control Manuals”) or any modification/substitution thereof shall be deemed to be tests conforming to Good Industry Practice for quality assurance.

- The Authority’s Engineer shall test check at least 50 (fifty) percent of the quantity or number of tests prescribed for each category or type of test for quality control by the Contractor.

- The timing of tests referred to in Paragraph 4 (ix), and the criteria for acceptance/ rejection of their results shall be determined by the Authority’s Engineer in accordance with the Quality Control Manuals. The tests shall be undertaken on a random sample basis and shall be in addition to, and independent of, the tests that may be carried out by the Contractor for its own quality assurance in accordance with Good Industry Practice.

- In the event that results of any tests conducted under Clause 11.10 establish any Defects or deficiencies in the Works, the Authority’s Engineer shall require the Contractor to carry out remedial measures.

(xiii) 	The Authority’s Engineer may instruct the Contractor to execute any work which is urgently required for the safety of the Project Highway, whether because of an accident, unforeseeable event or otherwise; provided that in case of any work required on account of a Force Majeure Event, the provisions of Clause 21.6 shall apply.

- In the event that the Contractor fails to achieve any of the Project Milestones, the Authority’s Engineer shall undertake a review of the progress of construction and identify potential delays, if any. If the Authority’s Engineer shall determine that completion of the Project Highway is not feasible within the time specified in the Agreement, it shall require the Contractor to indicate within 15 (fifteen) days the steps proposed to be taken to expedite progress, and the period within which the Project Completion Date shall be achieved. Upon receipt of a report from the Contractor, the Authority’s Engineer shall review the same and send its comments to the Authority and the Contractor forthwith.

- The Authority’s Engineer shall obtain from the Contractor a copy of all the Contractor’s quality control records and documents before the Completion Certificate is issued pursuant to Clause 12.2.

- Authority’s Engineer may recommend to the Authority suspension of the whole or part of the Works if the work threatens the safety of the Users and pedestrians. After the Contractor has carried out remedial measure, the Authority’s Engineer shall inspect such remedial measures forthwith and make a report to the Authority recommending whether or not the suspension hereunder may be revoked.

- In the event that the Contractor carries out any remedial measures to secure the safety of suspended works and Users, and requires the Authority’s Engineer to inspect such works, the Authority’s Engineer shall inspect the suspended works within 3 (three) days of receiving such notice, and make a report to the Authority forthwith, recommending whether or not such suspension may be revoked by the Authority.

- The Authority’s Engineer shall carry out, or cause to be carried out, all the Tests specified in Schedule-K and issue a Completion Certificate, as the case may be. For carrying out its functions under this Paragraph 4 (xviii) and all matters incidental thereto, the Authority’s Engineer shall act under and in accordance with the provisions of Article 12 and Schedule-K.

- Maintenance Period

- The Authority’s Engineer shall aid and advise the Contractor in the preparation of its monthly Maintenance Programme and for this purpose carry out a joint monthly inspection with the Contractor.

- The Authority’s Engineer shall undertake regular inspections, at least once every month, to evaluate compliance with the Maintenance Requirements and submit a Maintenance Inspection Report to the Authority and the Contractor.

- The Authority’s Engineer shall specify the tests, if any, that the Contractor shall               carry out, or cause to be carried out, for the purpose of determining that the Project  Highway is in conformity with the Maintenance Requirements. It shall monitor and  review the results of such tests and the remedial measures, if any, taken by the  Contractor in this behalf.

- In respect of any defect or deficiency referred to in Paragraph 3 of Schedule- E, the Authority’s Engineer shall, in conformity with Good Industry Practice, specify the permissible limit of deviation or deterioration with reference to the Specifications and Standards and shall also specify the time limit for repair or rectification of any deviation or deterioration beyond the permissible limit.

- The Authority’s Engineer shall examine the request of the Contractor for closure of any lane(s) of the Project Highway for undertaking maintenance/repair thereof, and shall grant permission with such modifications, as it may deem necessary, within 5 (five) days of receiving a request from the Contractor. Upon expiry of the permitted period of closure, the Authority’s Engineer shall monitor the reopening of such lane(s), and in case of delay, determine the Damages payable by the Contractor to the Authority under Clause 14.5.

- Determination of costs and time

(i) 	The Authority’s Engineer shall determine the costs, and/or their reasonableness,

that are required to be determined by it under the Agreement.

(ii) 	The Authority’s Engineer shall determine the period of Time Extension that is required to be determined by it under the Agreement.

(iii) 	The Authority’s Engineer shall consult each Party in every case of determination in accordance with the provisions of Clause 18.5.

6. 	Payments

(i) 	The Authority’s Engineer shall withhold payments for the affected works for which the Contractor fails to revise and resubmit the Drawings to the Authority’s Engineer in accordance with the provisions of Clause 10.2 (iv) (d).

(ii) 	Authority’s Engineer shall –

(a) 	within 10 (ten) days of receipt of the Stage Payment Statement from the Contractor pursuant to Clause 19.4, determine the amount due to the Contractor and recommend the release of 90 (ninety) percent of the amount so determined as part payment, pending issue of the Interim Payment Certificate; and

(b) 	within 15 (fifteen) days of the receipt of the Stage Payment Statement referred to in Clause 19.4, deliver to the Authority and the Contractor an Interim Payment Certificate certifying the amount due and payable to the Contractor, after adjustments in accordance with the provisions of Clause 19.10.

(iii) 	The Authority’s Engineer shall, within 15 (fifteen) days of receipt of the Monthly Maintenance Statement from the Contractor pursuant to Clause 19.6, verify the Contractor’s monthly statement and certify the amount to be paid to the Contractor in accordance with the provisions of the Agreement.

(iv) 	The Authority’s Engineer shall certify final payment within 30 (thirty) days of the receipt of the final payment statement of Maintenance in accordance with the provisions of Clause 19.16.

7. 	Other duties and functions

The Authority’s Engineer shall perform all other duties and functions as specified inthe Agreement.

8. 	Miscellaneous

- A copy of all communications, comments, instructions, Drawings or Documents sent by the Authority’s Engineer to the Contractor pursuant to this TOR, and a copy of all the test results with comments of the Authority’s Engineer thereon, shall be furnished by the Authority’s Engineer to the Authority forthwith.

- The Authority’s Engineer shall retain at least one copy each of all Drawings and Documents received by it, including ‘as-built’ Drawings, and keep them in its safe custody.

- Within 90 (ninety) days of the Project Completion Date, the Authority’s Engineer shall obtain a complete set of as-built Drawings, in 2 (two) hard copies and in micro film form or in such other medium as may be acceptable to the Authority, reflecting the Project Highway as actually designed, engineered and constructed, including an asbuilt survey illustrating the layout of the Project Highway and setback lines, if any, of the buildings and structures forming part of Project Facilities; and shall hand them over to the Authority against receipt thereof.

- The Authority’s Engineer, if called upon by the Authority or the Contractor or both, shall mediate and assist the Parties in arriving at an amicable settlement of any Dispute between the Parties.

- The Authority’s Engineer shall inform the Authority and the Contractor of any event of Contractor’s Default within one week of its occurrence.

Schedule – O

(See Clauses 19.4 (i), 19.6 (i), and 19.8 (i))

Forms of Payment Statements

1. 	Stage Payment Statement for Works

The Stage Payment Statement for Works shall state:

(a) 	The estimated amount for the Works executed in accordance with Clause 19.3(i) subsequent to the last claim;

(b) 	Amounts reflecting adjustments in price for the aforesaid claim;

(c) 	The estimated amount of each Change of Scope Order executed subsequent tothe last claim;

(d) 	Amounts  reflecting adjustment in price, if any, for (c) above in accordance with the provisions of Clause 13.2 (iii) (a);

(e) 	Total of (a), (b), (c) and (d) above;

(f) 	Deductions:

- Any amount to be deducted in accordance with the provisions of the Agreement

except taxes;

ii.      Any amount towards deduction of taxes; and

iii.    Total of (i) and (ii) above.

(g) 	Net claim: (e) – (f) (iii);

(h) 	The amounts received by the Contractor upto the last claim:

i.     For the Works executed (excluding Change of Scope orders);

ii.    For Change of Scope Orders, and

- Taxes deducted

2. 	Monthly Maintenance Payment Statement

The monthly Statement for Maintenance Payment shall state:

(a) 	The monthly payment admissible in accordance with the provisions of the Agreement;

(b) 	The deductions for maintenance work not done;

(c) 	Net payment for maintenance due, (a) minus (b);

(d) 	Amounts reflecting adjustments in price under Clause 19.12; and

(e) 	Amount towards deduction of taxes

3. 	Contractor’s claim for Damages

Note :-  The Contractor shall submit its claims in a form acceptable to the Authority.

Schedule – P

(See Clause 20.1)

Insurance

- Insurance during Construction Period

(i) 	The Contractor shall effect and maintain at its own cost, from the Appointed Date till the date of issue of the Completion Certificate, the following insurances for any loss or damage occurring on account of Non Political Event of Force Majeure, malicious act, accidental damage, explosion, fire and terrorism:

(a) 	insurance of Works, Plant and Materials and an additional sum of [15 (fifteen)] per cent of such replacement cost to cover any additional costs of and incidental to the rectification of loss or damage including professional fees and the cost of demolishing and removing any part of the Works and of removing debris of whatsoever nature; and

(b) 	insurance for the Contractor's equipment and Documents brought onto the Site by the Contractor, for a sum sufficient to provide for their replacement at the Site.

(ii) 	The insurance under sub para (a) and (b) of paragraph 1(i) above shall cover the Authority and the Contractor against all loss or damage from any cause arising under paragraph 1.1 other than risks which are not insurable at commercial terms.

- Insurance for Contractor's Defects Liability

The Contractor shall effect and maintain insurance cover of not less than 15% of the Contract Price for the Works from the date of issue of the Completion Certificate until the end of the Defects Liability Period for any loss or damage for which the Contractor is liable and which arises from a cause occurring prior to the issue of the Completion Certificate. The Contractor shall also maintain other insurances for maximum sums as may be required under the Applicable Laws and in accordance with Good Industry practice.

- Insurance against injury to persons and damage to property

- The Contractor shall insure against its liability for any loss, damage, death or bodily injury, or damage to any property (except things insured under Paragraphs 1 and 2 of this Schedule or to any person (except persons insured under Clause 20.9), which may arise out of the Contractor's performance of this Agreement. This insurance shall be for a limit per occurrence of not less than the amount stated below with no limit on the number of occurrences.

The insurance cover shall be not less than: Rs. 22.50 Crore[Contract Price]

(ii) 	The insurance shall be extended to cover liability for all loss and damage to the Authority's property arising out of the Contractor’s performance of this Agreement excluding:

(a) 	the Authority's right to have the construction works executed on, over, under, in or through any land, and to occupy this land for the Works; and

(b) 	damage which is an unavoidable result of the Contractor's obligations to execute the Works.

4. 	Insurance to be in joint names

The insurance under paragraphs 1 to 3 above shall be in the joint names of the Contractor and the Authority.

Schedule-Q

(See Clause 14.10)

Tests on Completion of Maintenance Period

- Riding Quality test:

Riding quality test: Riding quality of each lane of the carriageway shall be checked with the help of a calibrated bump integrator and the maximum permissible roughness for purposes of this Test shall be [2,200 (two thousand and two hundred only)] mm for each kilometre.

- Visual and physical test:

The Authority’s Engineer shall conduct a visual and physical check of construction to determine that all works and equipment forming part thereof conform to the provisions of this Agreement. The physical tests shall include measurement of cracking, rutting, stripping and potholes and shall be as per the requirement of maintenance mentioned in Schedule-E.

Schedule-R

(See Clause 14.10)

Taking Over Certificate

I, ……………………. (Name and designation of the Authority’s Representative) under and in accordance with the Agreement dated ………… (the “Agreement”), for‘Construction Of Rcc Crash Barrier Between  Main Carriageway And Service Road In    Km.281.600 To Km. 307.600,  Of N.H. 53 (Old N.H.06) In Chhattishgarh State Under Road Safty Work

through …………………. (Name of Contractor), hereby certify that the Tests on completion of Maintenance Period in accordance with Article 14 of the Agreement have been successfully undertaken to determine compliance of the Project Highway with the provisions of the Agreement and I hereby certify that the Authority has taken over the Project highway from

the Contractor on this day.........

SIGNED, SEALED AND DELIVERED

(Signature)

(Name and designation of Authority’s Representative)

(Address)

*******End of Document*******